## Cover
Whole Electricity System Coordination register for National Grid
Period 01/04/2023 to 31/03/2024 - published May 2024
Contact details
Any comments on the content of the register would be welcomed, along with any suggestions for future improvements. Any questions or requests relating to the information provided in the spreadsheet should be sent to:
nged.networkstrategy@nationalgrid.co.uk

## Overview
Whole system coordination register for National Grid published May 2024
This register is published to demonstrate compliance by National Grid electricity network licensees with the Whole Electricity System Licence condition.
It reports on compliance for licensees National Grid Electricity Transmission Plc (company number 2366977), National Grid Electricity Distribution (East Midlands) Plc (company number 02366923), National Grid Electricity Distribution (West Midlands) Plc (company number 03600574), National Grid Electricity Distribution (South West) Plc (company number 02366894) and National Grid Electricity Distribution (South Wales) Plc (company number 02366985) for the period for the period 1st April 2023 to 31st March 2024.
Whole electricity system outcomes arise from actions taken between two or more parties, at least one of whom holds an electricity transmission or distribution licence, that result in both:
• An investment in the transmission and distribution electricity networks representing best value for money; and
• Improving or, at a minimum, maintaining the services and benefits received by Customers of the electricity network.
Part A | The behaviour requirements (summarised)
Clause 1 | The licensee must coordinate and cooperate with other Electricity Distributors and transmission licensees to identify actions and processes that advance the efficient and economical operation of the Total System.
Clause 2 | The licensee must consider actions proposed by Distribution System Users/Transmission System Users which seek to advance the efficient and economical operation of its network.
Clause 3 | The licensee must use all reasonable endeavours to implement actions and processes identified and proposed through coordination or user suggestions that: (a) will not negatively impact its network; and (b) are in the interest of the efficient and economical operation of the Total System.
Part B | Demonstrating compliance (summarised)
This register details completed and in progress work which demonstrates compliance with the Whole System Electricity Licence Condition.
The licensee must prepare and is required to publish on its website a coordination register demonstrating the steps it has taken to comply with Part A of this condition not later than 27 May 2024.
The licensee must keep up to date and is required to publish its coordination register (as updated) on its website at least once every 12 months from the date of initial publication.
Further information on the Whole Electricity System Licence Condition and its purpose can be found on Ofgem's website.
Decision to implement the Whole Electricity System Licence Condition D17/7A for Transmission Owners and Electricity Distributors ¦ Ofgem

## Guidance
Guidance
1 | Where a licensee is collaborating for whole system benefit but NOT with another electricity network licensee, should or can this be included within the register? e.g. if a licensee is working with any of a local / regional authority (cross-sector), transport network or gas network for whole system benefit on combined network planning, could/ should this be included? a) if no other electricity licensees included? b) if no specific proposal has come from the organisation as a ‘system user’, but this is part of effective cooperation and coordination for whole system benefit.
Yes, this can be included. It is not required by the licence which sets a floor for demonstrating compliance, but is consistent with the spirit of the licence condition, so licencees are encouraged to include.
2 | Can planned activities or actions be included in the register?
No, only once initiated. The register can also show activites and actions which are in progress, completed, abandoned and transferred into BAU.
3 | How should the 'Activities and actions' tab be completed?
The 'Activities and actions' tab of the register is structured with coordination/ cooperation activities described in columns E-P, and related actions in the following rows in columns Q-T. If you are filling in an activity, columns Q-T are blocked out and for related actions, columns E-P are blocked. Choosing a 'Type' in column A as 'Coordination and cooperation activity' or 'Related Action' will indicate which columns should be completed. As required, you can choose 'Type', copy to insert rows, or delete rows. Actions can be repeated if common to more than one activity. However, if an action is being repeated, please refer (link) to the cell instead of copy-pasting.
4 | Can the template be altered?
The template has been agreed by all electricity network licensees, working together via the Energy Networks Association. The headings/ dropdowns should not be altered, but licensees may add their own branding to the 'Overview' tab, and alter the font sizes, column widths, freeze panes and magnification in the register to display the content better.
The template will be reviewed after the first publication and two years later.
5 | Should the register refer to specific projects?
The register should describe the coordination/ cooperation activity i.e. do X. While the description may refer to projects or programmes that deliver that coordination activity, the description should not lead with the project or programme name. One project or programme may include multiple coordination and cooperation activities.

## Activities and actions
The ‘activities and actions’ tab of the register is structured with coordination/ cooperation activities described in columns E-P, and related actions in the following rows in columns Q-T. If you are filling in an activity, columns Q-T are blocked out and for related actions, columns E-P are blocked. Choosing a ‘Type’ in column A as ‘Coordination and cooperation activity’ or ‘Related Action’ will indicate which columns should be completed. As required, you can choose ‘Type’, copy to insert rows, or delete rows. Actions can be repeated if common to more than one activity. However, if an action is being repeated, please refer (link) to the cell instead of copy-pasting. |  |  |  |  | Relevant coordination and cooperation activities | [11 empty] | Actions or Processes arising
| Unique identifier for each row of the sheet. xxxx/00n for an activity xxxx/00n/A0m for action xxxx refers to the publishing organisation or license group; n and m refers to numbers | Unique identifier for each row of the sheet. xxxx/00n for an activity xxxx/00n/A0m for action xxxx refers to the publishing organisation or license group; n and m refers to numbers | Lead licensee for the action or activity (not licence group) | Licensees and other stakeholders with whom collaboration was/is being carried out. | Details of the activity (could be an activity from a project or an activity that is used in multiple projects) along with its objective. Only activities that improve the economy and efficient of the whole electricity system is to be considered. Register is of activities in progress or completed, not planned. Explanation of the activity takes precedence over the project description. | In progress, Not taken forward, Complete | Latest stage / Update since the last publication / comments | When was a decision made to act upon a challenge/need. This could include the date when analysis for options was initiated. | Details of why it is relevant to whole system. | Links to reports of the project or activity | Description of any data that was shared. Include the format of the data, if applicable, and highlight any data that cannot be widely shared due to commercial sensitivity. | Links to the data not the project/activity | A brief description of the impact of the activity on the whole system, mainly along the lines of positive, neutral or negative | A brief description of the impact of the activity on the licensee, mainly along the lines of positive, neutral or negative | What is the recommended next stage? Positively, this activity would result in actions/processes that will then move on to the 'actions from coordination' sheet. If it is not taken forward, add justification. | Justification for the decision. Even if the decision is not to take things forward, a brief explanation should be added to promote learning. | Details of the action and/or process | Rough date of initiation of the action/process | New, Improving, Mature, BaU | Reference to the activity in the register that resulted in this action/process (not to be confused with internal order or project numbers)
Type | NGED Unique ID | NGET Unique ID | Licensee | Collaborating licensees and other stakeholders | Description of the coordination/ cooperation activity | Status | Latest stage /Update /comments (if any) | Coordination activity initiation date (mm/yyyy) | Whole system relevance of the activity | External links to reports on the activity (If available) | Description of data (who shared the data) [widely shared/restricted sharing] | External links for data (if available) | Impact of the activity on the whole system | Impact of the activity on licensee | Recommended next stage of the activity | Justification for recommendation | Action or Process description | Action or process initiation date (mm/yyyy) | Status | Reference of the activity or user suggestion which resulted in this action/process
Coordination and cooperation activity | NGED/0001 | NGET/0001 | ESO | NGED, ESO, TOs and all DNOs | CMP298 CUSC and CM080 STC modifications to undertake Distribution Impact Assessments. Providing an updated Statement of Works process for impacts on connections on one network upon another. 22/23 focus is the setting up of a working group to move to the new Transmission Impact Assessment (TIA) process. This was approved by Ofgem in January 2024 and the CUSC has been updated to reflect this process. | Complete | Code modification approved, TOs and DNOs working to implement the new Transmission Impact Assessment mechanism and rollout of Appendix G's everywhere | 2018-04-23 | Enabling better understanding of impacts across the Whole System of connections through codification of the more efficient "Appendix G" aggregated assessment methodology that NGED have been comprehensively utilising across all GSPs. | https://www.nationalgrideso.com/industry-information/codes/connection-and-use-system-code-cusc-old/modifications/cmp298-updating | A link to the Appendix G trial data that NGED publish on a monthly basis for all GSPs (unless in Project Progression). This includes the materiality headroom and fault level headroom at each GSP. | National Grid - Appendix G overview | Positive as it improves the Whole System coordination of connections, reducing the overall time it takes customers to hear back regarding a Statement of Works. | Improved process for completing Statement of Works and Transmission Impact Assessments | Continue to implement new CUSC CMP298 requirement and TO and DNOs to work closely to enable this | Improved Statement of Works will support improved Whole Systems understanding.
Related action | NGED/0001/A01 | N/A | NGED | [13 empty] | NGED have already proactively rolled out Appendix G at all our required GSPs prior to the requirement. We will review the status of all GSP Appendix G status and we are in the process of moving across to Mark 3 Appendix G's to better facilitate the management of the T-D queue. | 2024-01-18 | New | NGED/0001
Related action | N/A | NGET/0001/A01 | NGET | [13 empty] | NGET are in the processing of implementing revised Appendix TOG content into our TOCOs for all DNO’s existing agreements by 8/1/2026 in line with the implementation approach agreed by Ofgem. | 2024-01-01 | New | NGET/0001
Coordination and cooperation activity | NGED/0002 | NGET/0002 | ESO | NGED, ESO, all DNO's and TOs | CMP328 CUSC modifications was aimed at implementing a formal Distribution Impact Assessments (DIA)and provisions of a third party works proposal to resolve issues where a transmission connection can impact the distribution system. | Not taken forward | This CUSC modification has been withdrawn as it has been superseded by TMO4+ and will be included in the wider Connection Reform activity | 2019-12-11 | Enabling processes to allow third party resolution of Whole System issues where transmission connections require a distribution impact assessment. | https://www.nationalgrideso.com/industry-information/codes/connection-and-use-system-code-cusc-old/modifications/cmp328-connections |  |  | Currently there is no mechanism in the CUSC covering the arrangements for assessing the impact on the distribution network for a transmission connection. | Will ensure clear contractual arrangements are in-place so that transmission connection customers triggering a Distribution Impact Assessment are correctly assessed. This will remove the limitations of the Third Party Works (TPW) process. The proposed CUSC change will include timescales for issuing the relevant offers back to ESO. This will align with DNO Guaranteed Standard (GS) timescale to ensure queue position. | Take valuable learning from working group and ensure that it feeds into the equivalent process as part of Connection Reform | From a Whole System perspective, it is important to have the appropriate contractual relationships in place which reflect the shared responsibilities which are needed to deliver a coordinated and efficient electricity system.
Related action | NGED/0002/A01 | N/A | NGED | [13 empty] | Proactively asking ESO for information on where transmission customers require Third Party Works (TPW) to ensure they have had an appropriate distribution assessment. An interim measure until the Distribution Impact Assessment (DIA) is implemented via another CUSC modification or the wider Connection Reform | 2022-05-01 | BaU | NGED/0002
Coordination and cooperation activity | NGED/0003 | NGET/0003 | ENA | NGED, ESO, all DNO's, TOs, GDO and GTO | Energy Networks Association (ENA) Open Networks work stream activity including: - Standard flexibility products - Standard contract - Standard registration questions - Standard settlement processes - Standard dispatch API (system interface) - ESO/DSO Primary for services - Operational data sharing | In progress | Group Meetings are Ongoing with an annual agenda established, most recent reports are available in the links provided. A report for local area energy planning (LAEP) was published in Dec 2023. It explains how network operators can support local government to develop and deliver local net zero plans and projects. Strategic Connections Group: ENA working group created to develop tactical improvements to the connections process which can be implemented rapidly (from Summer 23). The group's aim is to improve customer experience and resolve the long connection lead times currently faced by customers nationally. Key focus areas include assessing how storage is treated to align with ESO initiatives and to introduce technical limits at the T-D boundary which allow customers behind these limits to connect non-firm. | 01/01/2022 (refreshed every year) | Enabling various initiatives to be produced to facilitate Whole System activities. Examples of Whole System outcomes include: * Whole System CBA * Operational data sharing * Local Whole System optioning service * Queue management and interactivity | https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ Work Stream 1B Link: https://www.energynetworks.org/creating-tomorrows-networks/open-networks/whole-electricity-system-planning Work Stream 3 Link: https://www.energynetworks.org/creating-tomorrows-networks/open-networks/distribution-system-operation-transition Work Stream 4 Link: https://www.energynetworks.org/creating-tomorrows-networks/open-networks/whole-energy-systems | working groups are looking at how data can be more readily shared between networks in formats that can be used by all. | https://www.energynetworks.org/industry-hub/resource-library/open-networks-2019-ws1b-p4-data-scope-final-report.pdf | Improved co-ordination of data and activities across networks to better understand whole energy system options and alternatives | supporting development of products to improve coordination across networks | continue with the ENA process and adopt relevant products to improve Whole System co-ordination | The ENA activities are a relevant coordination forum across all networks to improve whole system coordination.
Coordination and cooperation activity | NGED/0005 | NGET/0007 | NGET | NGED, NGET, SPEN and Welsh Government | Wales has effectively two electricity systems consisting of transmission and distribution split north and south with limited interconnection. The need to decarbonise will lead to increases of demand within the whole of Wales including the central areas we are working together to consider the best Whole System solutions to satisfy demand changes. | In progress | Development of options to manage demand changes to 2050. | 2021-09-13 | To best deliver for the people of Wales solutions that adapt to changes of demand for all communities is important. | https://www.gov.wales/welsh-government-and-network-operators-work-together-plan-uk-first-integrated-energy-grid-net-zero https://www.gov.wales/future-energy-grids-wales-reports | N/A | N/A | This will provide a positive solution to the Whole System requirements across the whole of Wales. | this will require ongoing coordination between NGET and the two DNO licence areas to establish the best Whole System solution for all Wales. | NGET and DNOs will propose a coordinated solution during 2024. | By considering demand growth predications and solutions between all parties a Whole System solution can be identified.
Coordination and cooperation activity | NGED/0006 | NGET/0009 | NGET | NGED | NGET is working on network updating in the South West area. NGETs Hinkley C Connection Project has utilised existing NGED infrastructure routes to minimise the impact of our new infrastructure. We have removed sections of NGED overhead lines and replaced capacity with substations and cables. | In progress | Project is in construction with majority of works to replace NGED capacity approaching completion North OHL section due for energisation by the end of 2024. | 2014-05-30 | Consideration of the Whole system impacts across South West and developing the Whole System solutions that deliver the best value inline with our obligations. | https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/hinkley-connection | N/A | N/A | This will enable the connection net zero generation Providing Whole System Solutions in the support of Net Zero. | This is appropriate approach to ensure infrastructure delivers the best Whole System solution across the Whole Electricity System | This work is due to complete ahead of the connection of Hinkley C Power Station. | The infrastructure is required to deliver Net Zero and our obligations drive us to achieve effective Whole System Solutions.
Related action | NGED/0006/A01 | N/A | NGED | [13 empty] | Sanford GSP has been energized and connected to NGEDs network. Consideration of the Whole system impacts across South West and developing solutions that deliver the best value in-line with our obligations. Through utilisation of NGED's assets the overall cost of the project has been reduced. | 2023-03-15 | BaU | NGED/0006
Related action | N/A | NGET/0009/A01 | NGET | [13 empty] | NGET has successfully energised 36 T-pylons between Bridgwater and Loxton in Somerset. | 2023-03-01 | BaU | NGET/0009
Related action | N/A | NGET/0009/A02 | NGET | [13 empty] | NGET has installed overhead conductors on all 116 of new T-pylons. | 2024-04-01 | BaU | NGET/0009
Coordination and cooperation activity | NGED/0007 | NGET/0012 | NGED, NGET | ESO, DNOs and TOs | In developing register, we have liaised with other networks to ensure we have captured all relevant Whole Systems information. | Complete | Annual Process | 2024-04-01 | Ensure Coordination of Whole System information and creation of the coordination register template to help facilitate alignment across licensees. | N/A | N/A | N/A | Ensuring existing Whole System information is captured | Assist in the development of coordination register | Annual process | To produce annual coordination register
Coordination and cooperation activity | NGED/0008 | NGET/0016 | NGED, NGET, NGG, W&WU | NGET, NGG, W&WU, NGED, universities and Suppliers | Zero2050 South Wales is a project to look at achieving south Wales net zero obligation before 2050 by considering Whole System solutions across all energy solutions. | Complete | Innovation Project / Report for this project (WP5 Industry) published on website report page | 2018-11-01 | How can the major industrialised areas of South Wales decarbonise considering a Whole Energy System Approach | https://www.zero2050.co.uk/ | N/A | N/A | Consideration of a coordinated approach to the decarbonisation of industrial areas of South Wales. | This project will support alternative options and consideration of decarbonising south Wales | Project is brought to a conclusion. Recommendations to progress certain aspects in the follow-up projects. E.g. (Accurately shape and define the assumptions used in the next phase of the IDC programme.) (Please see report: www.zero2050.co.uk/media/1269/wp5-industry-report.pdf) | Infrastructure development will be key to the development of a successful roadmap programme and hence establishing how the SWIC Roadmap and the Zero2050 programme collaborate to optimise resources and outcomes is essential. Therefore the need to expand on the findings in this project.
Coordination and cooperation activity | NGED/0009 | NGET/0018 | NGET | NGET, NPG, UKPN and NGED | The North East and East Midlands is seeing a large increase in connections to renewable generation and interconnectors. NGET is working closely with all stakeholders to ensure infrastructure can be combined in the best Whole System approach. | In progress | Ongoing appraisal of infrastructure impacts and whole system contribution. These projects are now part of the Accelerated Strategic Transmission Investment (ASTI) projects. Ongoing discussions with stakeholders about whole system impacts and benefits. | 2020-09-30 | Consideration of the Whole system impacts across East Coast and developing the Whole System solutions that deliver the best value inline with our obligations. | https://www.easterngreenlink1.co.uk/ https://www.easterngreenlink2.co.uk/ https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/north-humber-to-high-marnham https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/grimsby-to-walpole https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/brinsworth-high-marnham-uprating https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/yorkshire-green https://www.ofgem.gov.uk/publications/decision-accelerating-onshore-electricity-transmission-investment | N/A | N/A | This will allow us to make more efficient and coordinated decisions, unlock whole systems opportunities, enable the connection of renewable and net zero generation, along with interconnections to Europe. | This approach will enable systematic upgrade of our electricity transmission network in the coming years to ensure it remains fit for future, resilient, intelligent and efficient to deliver net zero. | Continued development of infrastructure solutions coordinating across generation, regional stakeholders, directly connected customers and networks. | The infrastructure is required to deliver Net Zero and our obligations drive us to achieve effective Whole System Solutions.
Coordination and cooperation activity | NGED/0010 | NGET/0020 | NGET | NGED, other DNO and TOs | Digitalisation Strategy and Action Plan (DSAP) development of strategy to achieve digitisation across energy networks which allow better data access. | In progress | Development of NGET strategy, published in December 2022. The strategy and action plan was updated in 2023 | 2021-11-15 | This project will develop strategies across the whole electricity system for data and digital access between networks and stakeholders | https://www.nationalgrid.com/electricity-transmission/about-us/digitalisation-strategy-and-action-plan | N/A | N/A | Over time, this should make data access to evaluate whole system issues across networks much more effective. | Data and digitalisation are key enablers for unlocking the benefits of the energy transition and National Grid is committed to playing a leading role. We have published in 2022 setting out our long term implementation activities. | Implement strategy following the updates in 2023. | Opportunity to receive stakeholder feedback on strategy and refining implementation.
Coordination and cooperation activity | NGED/0004 | NGET/0044 | NGED | NGET | Development of GSP solutions (e.g. Choakford and Ferryside) to resolve identified network constraints, considering Whole System impacts to both NGET and NGED network. | In progress | Work ongoing with NGET to understand alternatives to maintain DNO system security requirements | 2022-10-01 | Considering transmission and distribution options across the network to provide the best Whole System solution. Learning from this collaborative development can be applied to other distribution and transmission interfaces. |  |  |  | This will ensure the best option is selected to give the effective Whole System solution. | Positive, as each organisation is looking for the best solution in the interest of customers Reducing overall time to connect and finding an optimal solution. | Consideration of joint optioneering | Optioneering looks at solutions on a common basis across both organisations to achieve the most effective solution.
Related action | NGED/0004/A01 | NGET/0045/A01 | NGED | ESO and NGET | [12 empty] | Connection Application submitted for Choakford GSP following Whole System workshop with NGET where the following was discussed: * Confirmation of high level scope of works for each party and responsibilities * High level project programme of works with some indicative timescales | 2023-05-01 | New | NGED/0004, NGET/0044
Related action | NGED/0004/A02 | NGET/0045/A02 | NGED | ESO and NGET | [12 empty] | Connection Application submitted for Ferryside GSP following Whole System workshop with NGET where the following was discussed: * Confirmation of high level scope of works for each party and responsibilities * High level project programme of works with some indicative timescales | 2023-05-01 | New | NGED/0004, NGET/0044
Coordination and cooperation activity | NGED/0011 | NGET/0045 | ESO | NGED, all DNOs, TOs, ESO and GDNs | Future Energy Scenario (FES) Network Forum held at regular intervals across the year to discuss long-term scenario forecasting. | In Progress | Annual Process | 2020-09-16 | This interaction ensures coordination of long-term strategic forecasting activities across the whole electricity and energy system. |  | DNOs share Distribution Future Energy Scenarios (DFES) and have early foresight to challenge and review Future Energy Scenarios (FES) data and assumptions provided by ESO. |  | Coordinated long-term forecasting between electricity networks, stakeholder benefit of consistency when comparing scenario projections of different networks. | Improved understanding and dissemination of forecasting activities between electricity networks. | Continue working within the forum | To produce annual scenario forecasts for distribution network planning.
Coordination and cooperation activity | NGED/0013 | NGET/0046 | NGED, ESO | NGED, ESO and NGET | Week 24/42 data exchange NGED share key network and forecasting data with the ESO as part of the Week 24 and 50 data exchange. The data shared by NGED provides the ESO and NGET with the data required to ensure they have sufficient visibility of what is happening and is projected to happen on the distribution network. The ESO/NGET provide data to NGED as part of the Week 42 data exchange, which has historically enabled NGED to accurately reflect the interaction with the transmission network. This data is required as part of the Standard Planning and Operating Code data required by the Grid Code on an annual basis. | as BaU | Annual Process | Ongoing | Effective data sharing between distribution and transmission is essential to ensure the efficient and coordinated development of the Whole Electricity System. |  | Data shared between NGED and ESO includes: * Existing peak demand for cardinal points * Forecast demand growth * Technical diagrams * Embedded Generation * Equivalent of NETS model for power system analysis * Demand Control including low frequency tripping Data not publicly available |  | The Week 42 data provides visibility of the transmission network that is required to design a coordinated and efficient distribution network. The Week 24 data provides transmission with visibility of the distribution network. | The existing data exchange guidance was created before the proliferation of Distributed Generation (DG) on the distribution network. See NGED/0014 which details the Grid Code 139 data exchange proposal that is looking at modernising this data exchange process. In the interim, NGED are requesting additional power system data beyond the Week 24/42 exchange to ensure we are continuing to design and operate a coordinated Whole Electricity System. More information on this can be found in NGED/0015. | Annual process | Required under Grid Code, but currently under review as part of the Grid Code 0139 change proposal.
Coordination and cooperation activity | NGED/0014 | NGET/0047 | ESO | NGED, NGET and all DNOs | Grid Code 0139 change proposal As detailed in NGED/0013, the existing week 24/42 data exchange no longer provides sufficient information to either the DNO or ESO/NGET. The Grid Code 0139 modification proposal is seeking to increase the scope and detail of the planning-data exchange between DNOs and ESO to help facilitate the transition to a smart, flexible whole energy system. This will be done by better aligning data exchanges and providing greater granularity. This GC change has progressed well in 23/24 and the scope and legal text have been largely agreed. | In progress | Group meetings are ongoing | 2020-02-01 | Improving alignment of data and increasing data granularity will increase visibility across the transmission and distribution interface. This increased visibility at the design and operational stage will mean improved integration of planning assumptions, which will result in a more efficient and coordinated network being developed. | https://www.nationalgrideso.com/industry-information/codes/grid-code-old/modifications/gc0139-enhanced-planning-data-exchange |  |  | Positive as it will increase Whole System coordination between DNOs and ESO/NGET. Which will provide benefits to customers through a more coordinated and efficient approach to designing networks. | Positive impact as it will increase the granularity, frequency and exchange format that data is shared between DNOs and ESO/NGET | Continue with process improvement | Existing Week 24/42 process is no longer fit-for-purpose and this Grid Code change proposal will enhance the existing process to ensure it meets the needs of DNOs and ESO/NGET.
Coordination and cooperation activity | NGED/0015 | NGET/0048 | NGED | ESO and NGET | The existing Week 42 data from ESO only provides an equivalent for a connected winter peak position (as detailed in NGED/0013). To enable future detailed Whole System studies on the highly interconnected South West 132 kV network, particularly as part of the ongoing Hinkley connection, NGED is requesting additional data to represent future positions and additional seasonal equivalent models. This coordination activity will be superseded by the Grid Code 0139 proposal detailed in NGED/0014. In addition to this, in 22/23 and 23/24 NGED have formally requested more detailed future transmission network positions and are working through the practicalities of this with ESO and NGET. | In progress | In discussion with NGET | 2022-01-01 | Enabler to strategic Whole Electricity System planning, particularly focussed on the connection of Hinkley C connection described in NGED/0006 activity. |  | Power system model data in either Power Factory or excel format. Representing future position of the transmission network for the staged connection of Hinkley C. NGED are currently in discussion with NGET for additional seasonal data. Data not publicly available. |  | Will allow more detailed strategic Whole Electricity System planning between the distribution and transmission network, particularly where there is a lot of interaction around the Hinkley C connection. | Positive impact as if only the Week 42 data was used for design purposes, credible network conditions could be missed at the design stage. Through proactively requesting the data from the NGET, alignment of the Whole Electricity System will result in a more coordinated and efficient future network position. | NGED will request period refresh until Grid Code 0139 change proposal is implemented | Required to supplement Week 42 data exchange.
Related action | NGED/0015/A01 | NGET/0048/A01 | NGED | NGET and ESO | [12 empty] | In addition to this, in 22/23 NGED have formally requested more detailed future transmission network positions and are working through the practicalities of this with ESO and NGET. This is an interim step to help with T-D planning until GC0139 comes into force. | 2022-01-01 | New | NGED/0015, NGET/0048
Coordination and cooperation activity | NGED/0017 | NGET/0049 | NGED | ESO, NGET | Implementation of the Appendix G trial as part of the Statement of Works (SoW) process. Due to the cumulative impact of connecting large volumes of new generation to the distribution system and the lengthy SoW process, a new trial SoW process is currently in place, known as the ‘Appendix G trial’. NGED has been instrumental in trailing this new process and the first DNO to have an Appendix G in place. Discussions are ongoing to look at moving all GSPs across to Mark 3 Appendix Gs to help with T-D coordination and Technical Limit rollout | as BaU | Ongoing |  | Improves Statement of Works process and distribution and transmission interface. | https://www.westernpower.co.uk/our-network/statement-of-works | Appendix G data shared includes: * Connected and accepted generation in each part (1-5) of the appendix G process * Materiality headroom * Fault level headroom | https://www.westernpower.co.uk/our-network/statement-of-works | The introduction of the Appendix G has reduced the time customers have to wait for the outcome of the process from around four months to six weeks. | NGED have been central to trialling and implementing the Appendix G trial process. NGED now use the Appendix G at all GSPs across all 4 licence areas. Increasing visibility to ESO of the connection pipeline and reducing overall time for them get a response. | Continue to codification as detailed in the CMP298 CUSC entry (NGED/0001) | Appendix G trial has been a success at improving the distribution and transmission Statement of Works process.
Coordination and cooperation activity | NGED/0025 | NGET/0050 | ESO | NGED, NGET | System HILP Event Demand Disconnection (SHEDD) was an NIA innovation project to determine the future options for Low Frequency Demand Disconnection (LFDD). | Complete | Project recommendations have now been made | 2020-04-01 | Under frequency disconnection resides on the DNO system and acts to preserve integrity of the overall electricity system. | https://www.westernpower.co.uk/innovation/projects/system-hilp-event-demand-disconnection-shedd | Data regarding the cost benefit of the different approaches was shared between WPD and ESO. |  | This project has enabled an updated thinking on the future strategy on the future of LFDD. The impact on the Whole System enables improved resilience during HILP events. | Requirement to implement changes identified as part of SHEDD project to ensure Whole Electricity System stability is maintained through keeping LFDD procedures appropriate for the changing network. | Discussion of the strategy options needs to be progressed at a whole industry level | As a critical Whole System backup to low frequency events, it is crucial that LFDD is reviewed and updated to meeting the changing network conditions and requirements.
Coordination and cooperation activity | NGED/0016 | NGET/0040 | NGED, ESO | NGED, ESO and NGET | Each NGED licence area has a monthly call with the ESO and NGET to discuss data exchange, Statement of Works (SoW), ongoing works and general NGED and NG interfaces. Every 6 months this is an in-person Joint System Design Liaison (JSDL) meeting. These are proving essential with the fast changing nature at distribution and transmission. | as BaU | Meeting for each NGED licence area at the beginning of each month and an in-person Joint System Design Liaison (JSDL). | Ongoing | This monthly engagement call between NGED, ESO and NGET provides a regular forum to collaborate and coordinate on Whole Electricity System challenges. |  | Primary data exchange is as part of the Statement of Works Appendix G process and Week 24/42, but regular ad-hic data sharing is facilitated through these cooperation meetings. |  | This regular forum provides a positive way of understanding and better aligning transmission and distribution challenges. | This forum has been very positive for NGED as it has effectively increased the speed at which interactions with National Grid are identified, discussed and resolved. | Continue with ongoing meetings | Has proven as an effective way of enabling Whole System planning.
Related action | NGED/0016/A01 | NGET/0040/A01 | NGED, NGET | ESO | [12 empty] | Through the monthly calls with ESO and NGET it was identified that distribution and transmission have different approaches to modelling customer behaviour. Particularly related to distributed generation and battery storage. Additional discussions and data sharing are ongoing to improve alignment to ensure coordination between transmission and distribution is aligned. Learning from this Whole System alignment can be applied to other DNO and transmission interfaces. This is really been drawn out in the Strategic Connection Group work and the ESO 5-point plan. | 2021 | Improving | NGED/0016, NGET/0040
Related action | NGED/0016/A02 | NGET/0040/A02 | NGED, NGET | ESO | [12 empty] | As CMP328 (NGED/0002) is still in the process of being implemented an interim process has been developed to enable the undertaking of Third Party Works (TPW) Distribution Impact Assessments (DIA) to understand the impact of Transmission customers on the Distribution network. On a periodic basis, ESO share the TPW data with each NGED licence area to enable the required DIA to be undertaken. | 2022-02-01 | New | NGED/0016, NGET/0040
Related action | NGED/0016/A03 | NGET/0040/A03 | NGED, NGET | ESO | [12 empty] | Discussed and agreed interim steps for sharing strategic power system models to ensure a coordinated Whole System approach is taken to designing the South West 132kV and Transmission networks. Particularly relating to the major works stated works associated with the connection of Hinkley Point C nuclear power station. Monthly calls also provided forum to provide feedback on the commercial assumptions and charging arrangements relating to Hinkley Point C. | 2018-01-01 | Improving | NGED/0016, NGET/0040
Related action | NGED/0016/A04 | NGET/0040/A04 | ESO | NGED, NGET | [12 empty] | Collaboration between ESO, NGET and NGED to better understand how ANM will operate at infrastructure sites. Implementation of an infrastructure ANM scheme will not only benefit NGED's customers by providing alternatives to conventional reinforcement, but will also provide value to other connecting licensees. Also collaborating on understanding with ESO the asset reclassification for ANM and changes in responsibility to understand Whole Electricity System impact and ensure DNO and NGET remain compliant, particularly as tertiary connections increase. Focus for last year was on technical AMN limits to ensure transmission stability. | 2021-09-22 | New | NGED/0016
Related action | NGED/0016/A05 | NGET/0040/A04 | NGED, ESO, NGET | NGED, ESO, NGET | [12 empty] | Additional coordination meetings and actions agreed following the monthly call. These include, but are not limited to: * Sharing data on battery storage contracts and operating regime * Interfaces with adjoining DNOs and coordinated data sharing as part of Week 24 and ongoing project progressions * TANM constraint discussions * Coordinated operational running arrangement changes on distribution or transmission to mitigate the need for conventional reinforcement * Resolution of thermal and fault level constraints at GSPS through conventional and RDP solutions. | 2021-04-01 | BaU | NGED/0016, NGET/0040
Coordination and cooperation activity | NGED/0036 | NGET/0051 | ESO | all DNOS, TOs | Whole electricity joint forum | Complete | The ESO ceased the forum in 23/24 | 2021-08-12 | A regular (monthly) forum for whole electricity system initiatives such the RDPs and other Projects. | This creates an opportunity to investigate new, emerging technologies that are able to reduce disruption, costs, and time, and which can more efficiently deliver the capacity that heating and transport electrification will demand. |  |  | DNO and TO input on the relevant ESO initiatives | DNO and TO input on the relevant ESO initiatives | review best way of engaging on relevant topics | The value of the forum is being reviewed by the ESO to identify the best way of collaborating
Coordination and cooperation activity | NGED/0037 | NGET/0052 | NGED, ESO | NGED, ESO, NGET | South West Operational Tripping Scheme To facilitate distribution connected generation in the South West, ESO and NGED have agreed a South West Operational Tripping Scheme (SWOTS) for an N-3 outage condition on the transmission network. SWOTS will automatically constrain the Customer’s generation output to zero during N-3 outage conditions on the National Electricity Transmission System (NETS). | Complete | The scheme has been made operational and is now live | 2016-01-01 | Enabling distribution customers to connect without the need to wait for transmission works or conventional reinforcement. |  | Captured as part of the Statement of Works (SOW) process. |  | Enabling distribution customers to connect without the need to wait for conventional reinforcement for an onerous transmission outage | Helps to enable connections onto the network | Development complete. Operation ongoing | Continue to operate the SWOTS
Coordination and cooperation activity | NGED/0040 | NGET/0053 | SSEN Transmission | All DNOs and TOs, ESO, ENA | DSO implementation plan and interactive road map | Complete |  | 2022-12-01 | As part of the ENA Open Network Project there was an objective to create an implementation plan and interactive roadmap for stakeholders showing the DNOs transitioning to DSOs. This was fed into and agreed by all DNOs, ESO and TO with the ENA coordinating. This looked at all functions of the DSO including system operation, markets, coordination, planning, flexibility services etc. SSEN Transmission fed into this by providing evidence on what we are doing to support the implementation of DSO and fed into the work to ensure that the Appropriate data exchange and coordination practices are in place to avoid any unintended consequences. | Open Networks: developing the smart grid - Energy Networks Association | Coordination with the ESO and DSO, system operation including restoration, network planning | https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ | Our work in this area allowed coordination across the whole electricity system to ensure that the implementation of DSO functions were coordinated effectively and that any concerns or unintended consequences were avoided | Positive impact on stakeholder collaboration and ensuring the safe reliable and economic operation of the transmission network as the use and operation of the whole system changes | Work within the ENA has now completed. This work is moving internally through collaborating regularly with SHEPD on their progress of implementing DSO functions and services | Important to monitor and feed into any changes that may affect the safe, reliable and economic operation of the transmission network.
Coordination and cooperation activity | NGED/0021 | NIA | All | all DNOs, ENA, ESO (when relevant), Ofgem (when relevant) | Whole System Future Energy Scenarios (FES) building blocks. This has evolved into the Open Networks forecasting forum - DNOs and guests | Complete | This is a business as usual process established in Open Networks Workstream 1B Product 2. BaU meeting, used to run regularly and was recently reinstated to be every 2 weeks due to major developments around FES and RESP. Discussions of changes to the DSO forecasting outputs and creating DNO statements and views on new developments e.g. FES changes, RESP | 2020-12-31 | This process considers data exchange at transmission-distribution interfaces between DSO DFES - ESO FES for agreed forecasting components, e.g. EV and heat pump volumes, electricity consumption etc. This information is used for further alignment of FES-DFES to support whole electricity system planning. Coordination across DNOs to ensure consistency | https://www.energynetworks.org/industry-hub/resource-library/open-networks-2020-ws1b-p2-coordination-of-national-and-regional-fes.pdf | Volumes of low carbon technologies including electric vehicles and heat pumps. Capacity of different types of distributed generation including wind farms, photovoltaics and gas fuelled flexible generators. Electricity consumption for domestic and non-domestic demand. All datasets per Grid Supply Point feeding area. | Links on FES and DFES can be found on ESO and DNO websites. | Positive impact as this process allows the alignment of long-term forecasts for demand and generation used for distribution planning (DFES) and transmission planning & national system operability (ESO FES). positive, coordinates DNOs to give consistent messaging on forecasting topics such as FES usage | Positive impact as this process allows the alignment of long-term forecasts for demand and generation used for distribution planning (DFES) and transmission planning & national system operability (ESO FES). Positive, ensures NGED can contribute to position statements and discussions | The recommended next stage is that the agreed building blocks are reviewed and updated by all DNOs and the ESO, on an annual basis. Continue engagement | The annual review of building blocks allows DNOs and the ESO to tailor the data exchange to forecasting components that are relevant to both distribution network planning, transmission planning and national system operability. Ensuring that NGED's views continue to be represented in the DNO statements and discussion with Ofgem and ESO.
Related action | NGED/0021/A01 | NIA | NGED | [13 empty] | This is an annual Whole System planning process, that informs the recalibration of forecasting scenarios used by DNOs for distribution network planning (DFES) and by the ESO for transmission planning and national system operability (FES). | 44196 | Mature | This is an annual Whole System planning process that was established in Open Networks WS1b P2.
Coordination and cooperation activity | NGED/0022 | NIA | ENWL, NGED | NGED, ENWL | Periodic meeting between NGED and ENWL. | In progress | Early stages of development | Regular meeting | Periodic meeting to discuss projects, processes and initiatives which work towards whole electrical system collaboration. |  |  |  | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | BaU | Helps to move the industry further towards Whole System.
Coordination and cooperation activity | NGED/0041 | NGET/0053 | NGET, UKPN, NGED | NGET, UKPN, NGED | Investigation in to the benefit of high temperature super conducting cables for transmission and distribution. | In progress | NGET awaiting progression to next stage | 2022-03-01 | This Discovery Phase project will investigate the feasibility of use of High Temperature Superconductor (HTS) cable technology to increase network capacity in the urban environment. Superconducting cables have three to ten times higher power density than conventional cable systems, meaning they deliver higher capacity at lower voltage levels and via a lower number of routes. | https://smarter.energynetworks.org/projects/10027601/ |  |  | If project is successful cables could be implemented system wide to improve efficiencies. | HTS technology will allow faster network capacity increase, delivering time, cost, and carbon savings with reduced energy losses and wider environmental benefits. | Ongoing
Coordination and cooperation activity | NGED/0046 | NGET/0054 | ENA | All DNO's, NGET and ESO | Actively inputting into the Strategic Connection Group (SCG) which is looking to address the existing 'first-come, first-served' approach, which is causing significant delays. The SCG is currently looking at 3 main actions: 1. Distribution Queue Management (QM) 2. Transmission and Distribution interface 3. Greater flexibility for storage distribution customers | In progress |  | 2022-12-01 | Creating clear and consistent boundaries between transmission and distribution. This will help manage the queue and accelerate customers with smaller, more agile projects. Distribution network operators working in coordination with ESO will be able to manage connections within agreed technical limits at each boundary point (known as a Grid Supply Point or ‘GSP’). Coordinated approach to how the queue is managed between transmission and distribution networks will be implemented for generation/exporting distributed energy resources (small scale generation and battery storage) that are still dependent on both transmission and distribution network capacity. | coordinated approach to how the queue is managed between transmission and distribution networks will be implemented for generation/exporting distributed energy resources (small scale generation and battery storage) that are still dependent on both transmission and distribution network capacity. | Data has been collated by all DNOs to input into the 3 immediate actions proposed. This includes schemes in the queue and transmission capacity secured. |  | If proposed Actions (see link to the left) it will help free up the significant queue and delays that customers are seeing. | Key to enabling connections First ready, first connected. Connections which reach agreed milestones will be prioritised for connection where there is no detrimental impact to others ahead of them in the queue. ‘ | Continue imputing into SCG and supporting in engagement with stakeholders and customers to drive forward quick win actions
Related action | NGED/0046/A01 | NGET/0054/A01 | ENA | All DNO's, NGET and ESO | [12 empty] | Starting this spring, Connections accepted prior to 2017 that are still in the connection queue will be identified and will follow a three step approach to migrate those projects to milestones or remove them from the queue. | 2022-12-01 | New | NGED/0046, NGET/0054
Related action | NGED/0046/A02 | NGET/0054/A02 | ENA | All DNO's, NGET and ESO | [12 empty] | Accelerate connections by offering standardised ‘non-firm’ connections that allow the networks to connect them more quickly. Standards and codes are being updated to allow this to happen without resulting in unintended costs and/or perverse incentives and no wider detriment to others. | 2022-12-01 | New | NGED/0046, NGET/0054
Related action | NGED/0046/A03 | NGET/0054/A03 | ENA | All DNO's, NGET and ESO | [12 empty] | Technical limits are to be defined to give DNOs clear boundaries, This will enable DNOs to accelerate connections within those boundaries. | 2022-12-01 | New | NGED/0046, NGET/0054
Related action | NGED/0046/A04 | NGET/0054/A04 | ENA | All DNO's, NGET and ESO | [12 empty] | Queue coordination across the whole system (joint t-d queue with agreed principles for accelerating customers up the queue where shovel ready) | 2022-12-01 | New | NGED/0046, NGET/0054
Related action | NGED/0046/A05 | NGET/0054/A05 | ENA | All DNO's, NGET and ESO | [12 empty] | Energy storage to be provided with non-firm access like generation export rather than being treated like conventional demand | 2022-12-01 | New | NGED/0046, NGET/0054
Coordination and cooperation activity | NGED/0047 | NGET/0005 | NGET | NGED | Development of Cellarhead GSP solutions considering Whole System impacts to both NGET and NGED network. | In progress | Work ongoing with NGED to understand alternatives to maintain DNO system security requirements | 2020-11-30 | Considering solutions across networks to provide the best Whole System solution. | https://www.nationalgrid.com/electricity-transmission/document/140876/download | N/A | N/A | This will ensure the best solution is selected to give the effective Whole System solution | Each organisation is looking for the best solution in the interest of consumers | Consideration of joint optioneering | Optioneering looks at solutions on a common basis across both organisations to achieve the most effective solution.
Coordination and cooperation activity | NGED/0048 | NGET/0027 | NGET | NGED | Plymouth long term optimisation planning. | Complete | Analysis complete, results shared with NGED and within NGET. | 2022-10-01 | Third case study for joint Tx and UHV Dx regional whole system planning and optimisation to 2050 | N/A | Output of activity including designs and conclusions shared with NGED and internally within NGET | N/A | Optimised Tx and 132 kV Dx design for 2050 Net Zero scenario. Proved that current 10 year reinforcement plan for area contributes efficiently to long term plan. | Helped to further improve the process and tools for 2050 long term whole system planning. | Licensees to continue with plan for reinforcement of the system in the short term and to consider how best to prepare for additional reinforcements in the design needed for 2050. | By designing short term reinforcements with longer term requirements in mind, cost and deliverability of longer term reinforcements are improved.
Coordination and cooperation activity | NGED/0049 | NGET/0028 | NGET | NGED | South-East Birmingham long term optimisation planning. | Complete | Analysis complete, results shared with NGED and within NGET. | 2022-05-01 | Second case study for joint Tx and UHV Dx regional whole system planning and optimisation to 2050 | N/A | Output of activity including designs and conclusions shared with NGED and internally within NGET | N/A | Optimised Tx and 132 kV Dx design for 2050 Net Zero scenario. Options for longer term plan considered by licensees for acceleration to meet shorter term requirements. | Helped to further improve the process and tools for 2050 long term whole system planning. | Licensees to consider options in 2050 design to meet requirements in 2020s in order to ensure long term efficiency in development of Tx and Dx systems. | These options could allow for a more deliverable solution in the short term and reduced cost and impact over the longer term.
Coordination and cooperation activity | NGED/0050 | NGET/0030 | NGET | NGED, NPg, SSE, UKPN, ENW, ESO & OFGEM, combined authorities | FNB (Future Network Blueprint) is a stakeholder approach to regional network planning. It's a tool that provides a way for working together with stakeholders in defining the future needs of the transmission network by combining their requirements with ours while recognising the specific and nuanced needs of different geographical areas. | In progress | Stakeholder events with every DNO, each of the combined authorities, 6 regional events were held in 2023. Follow up events are planned in May 2024. | 2023-02-27 | Future Network Blueprints will allow us to make more efficient and coordinated decisions, unlock whole systems opportunities, and surface where industry reform is needed to enable net zero | https://www.nationalgrid.com/electricity-transmission/how-our-future-network-blueprints-are-shaping-electricity-grid-tomorrow | N/A | N/A | A whole system approach to define and evolve the view of the future needs of the electricity transmission network with the input of stakeholders and considering the nuances of different regions | It will ensure NGET has a holistic regional and national view to how the future network should look. It will start shaping our strategies to help us shaping the regulatory investment plans. | Continue to discuss with all stakeholders and start to share the plan. | To increase the transparency of our plan and to ensure that network upgrades do not preclude collective regional decarbonisation plans.
Coordination and cooperation activity | NGED/0051 | NGET/0031 | NGET | NGED, NPg, SSE, UKPN, ENW, ESO, OFGEM & DESNZ | Winter Preparedness 2022/23. This activity was in response to ESO's Winter Outlook 2022/23: Early view, which includes an early view of the electricity security of supply outlook for winter. | Complete | This activity is completed. | 2022-06-01 | Part of the coordination group on activities for OC6 and ESEC optimisation process improvement and awareness of potential impacts to ensure winter security of supplies for whole system. | https://www.nationalgrideso.com/document/268346/download https://www.nationalgrideso.com/research-and-publications/winter-outlook | N/A | N/A | Undertook enhanced winter preparation to ensure whole system security and collaborated with ESO, all DNOs, ENA, Ofgem and DESNZ on enhanced demand security. | Positive - ensured network was more resilient for winter and prepared for extreme challenges. | Development in to annual approach. The outcomes can be applied as enhanced winter preparedness as BAU. | To continuously improve winter preparedness.
Coordination and cooperation activity | NGED/0052 | NGET/0032 | NGET | NGET, NGED | This project aims to investigate charging infrastructure and its impact on our network. It will produce models that will accurately assess the impact of a roll out of EV Trucks across our license areas. The key deliverables will be shared with all RIIO licensed UK DNOs for their own use. | In progress | Monthly Group Meetings are Ongoing | 2023-11-01 | The expected adoption of EVs is a challenge to all networks as they expect to plan network to facilitate the demand growth followed by the transport electrification. | https://smarter.energynetworks.org/projects/nia2_nget0051/ | No data shared from NGET. All publicly available. | N/A | Findings about the Megawatt charging system of eTrucks has the potential to help plan the charging of eTrucks and plan the strategy to role out for future infrastructures | This will help NGET to understand the increasing demand from transport electrification, especially on fast charging behaviours from electric trucks, to facilitate the network planning process to delay or avoid network investment. | Wider group collaboration and input is required and is essential to bring out the true benefits. | Feedback to be used to consider wider business requirements.
Related action | N/A | NGET/0033/A001 | NGET | NGET, SSE, SPEN | [12 empty] | NGET plans to launch an EIC call to understand our supply chain risks and dependencies will form a key part of any future disclosure and will inform our future approach to managing and setting appropriate targets for our biodiversity impacts across our business. While both of these initiatives are currently optional, we expect TNFD to become mandatory at some point in the future, in the same way as the Taskforce on Climate-related Financial Disclosures (TCFD). | 2024-03-01 | Mature | Following the UN Biodiversity Conference (COP15) and the subsequent approval of the Post 2020- Global Biodiversity Framework (GBF) in Dec 2022, there will be more stringent requirements on business to assess and disclose their impacts and dependencies on Biodiversity. Target 15 within the GBF requires businesses to assess and disclose biodiversity dependencies, impacts and risks along their operations, supply and value chains, and portfolios, and reduce negative impacts. This requirement is particularly relevant for large, transnational companies which would include National Grid.
Coordination and cooperation activity | NGED/0053 | NGET/0034 | NGET | ENW, NGED, ESO, SSEN-T, UKPN | Whole Energy System Resilience Vulnerability Assessment (WELLNESS) will provide core evidence and a consistent approach to develop resilience standards that inform whole energy decision making, which capture multi-energy flexibility, to create a cost-effective and consistent UK resilience strategy. | In progress | SIF Discovery Phase completed in July 2023. Partners are building a resilience demonstrator prototype to inform network decision making and resilience metrics. | 2023-04-01 | WELLNESS project will develop standardised, whole energy system assessment methodologies and systematic performance metrics which can allow resilience to be fully integrated across both operational and investment decision-making, across all electricity networks, then other energy networks. | Whole Energy System Resilience Vulnerability Assessment (WELLNESS) ¦ ENA Innovation Portal (energynetworks.org) | N/A | N/A | The definition of resilience and associated standards/metrics applied in a uniform manner across all energy networks yielding a robust resilient interconnected network with optimum investments. | There will be a standardised coordinated manner in quantifying resilience contribution from all ends (generation - distribution) as well as all energy networks will be able to justify and apply resilience-oriented funding/investments uniformly to avoid over/under investments. | Feedback, Stakeholder & Consultation Workshops on the way to a Beta deployment. | Need to understand blockers towards promotion into business as usual.
Coordination and cooperation activity | NGED/0054 | NGET/0036 | ESO | NGET, NGED, Welsh Government, CGI, SPEN, CENIN renewables ltd. | The Powering Wales Renewably Project is targeted at the Net-zero challenge. Collaboratively, local Government, network operators and customers, will identify priorities as to how the whole electricity network can innovatively enable Welsh decarbonisation plans, increase renewable electricity hosting, and deliver in the best interests of Wales’s citizens and their communities. | In progress | Use case 1 - Whole Welsh electricity Transmission and Distribution model for Wales (Digital Twin Poc), showing the existing network status and accepted connections and reinforcement. Use case 2 and 4 - High level design of procured flexibility coordination and integrated T/D planning against reformed connection queue. Lead partner is organising workshop for use case 1. | 2023-10-01 | The results from potential, flex coordination, curtailment, T/D planning for distribute energy resources (DER) will be utilised by Welsh government along with stakeholders especially local DER providers. | https://smarter.energynetworks.org/projects/10060474/ | N/A |  | Digital twin will be useful for all stakeholders | It will make the evaluation process easier for utilities and Welsh government | Workshop being held for the feedback from partners which will help to understand the use case and to update the digital twin as well the requirements for powering Wales renewably. | User case feedback is necessary to understand the requirements.
Coordination and cooperation activity | NGED/0055 | NGET/0037 | NGET | ESO, all DNOs and TOs | The Triton project is a project to build and deploy a 400/132kV planning and visualisation tool in NGET. It combines current GSP and BSP level demand, and corresponding demand growth forecasts e.g. from Neptune and FES, with transmission and distribution network GIS and LTDS data in a partly geospatial tool to inform whole system 400/132kV planning and engagement at regional and local scales by NGET with the relevant distribution network. The Neptune project is designed to help us identify the likely needs for England and Wales from a transmission basis, considering transport, domestic commercial and industrial space heating, industrial low grade and process heat demand growth and corresponding energy supply and storage growth. | In progress | Tool minimum viable product deployed and trial use in progress. | 2023-03-01 | This project looks at interactions with other energy vectors, including hydrogen and between transmission and distribution networks. It allows the modelling of different scenarios capturing the impact on the network for varying energy vector capacities. (For example considers the different requirements based upon blue and green hydrogen production) | N/A | N/A | N/A | To inform economic and efficient network planning for demand growth between TO and DNOs at 400/132kV at regional and local scales. The project considers the types of technologies required to deliver a whole system solution to 2050 and is looking to see how we can support the ESO pathfinder projects. | The project enhances the internal capability of NGET to consider whole system factors in transmission network development for regional and local demand growth. The project delivers insights about the likely future transmission network requirement to inform the economic and efficient development of the network by teams across NGET. | Project in progress - Working on further development and Phase 2 will officially commence on March 2024. | Gradual shift from a minimum viable product to a full functional product with improved capabilities and features.
Coordination and cooperation activity | NGED/0056 | NGET/0038 | NGET | All DNOs and TOs | Review of the network strategy design principles | In progress | Ongoing discussions to review the design principles for sustainability. Other design principles are also being developed including substation design with OMNIA project. | 2023-10-01 | It allows ET to standardise the design of substations of the future. | N/A | N/A | N/A | It will allow better capacity signalling for new customers, allow more sustainable substation design. Increase the interconnectivity of NGET's assets. | It will help ET to design substations with space to accommodate other future drivers e.g., operability assets (including for voltage control) or to connect new circuits of power flow control devices. | Continue working on the project
Coordination and cooperation activity | NGED/0057 | NGET/0041 | ESO | All DNOs, TOs and ENA | Reform of the GB connections arrangements in line with DESNZ/Ofgem's Connection Action Plan | In progress | ESO published their final recommendations for a new connections process in Dec 23. NGET are actively participating in further development of these proposals through the Connections Process Advisory Group (CPAG) and the Connections Delivery Board (CDB). Conclusion of 2024Q1 actions from the action plan due at the CDB on 21 March 2024. | 2023-11-01 | GB connections arrangements will impact all customers, both generation and demand and Transmission and Distribution level | https://www.nationalgrideso.com/industry-information/connections/connections-reform#Key-documents https://assets.publishing.service.gov.uk/media/655dd873d03a8d001207fe56/connections-action-plan.pdf | N/A | N/A | Positive impact on customers and their connection timescales. Those progressing their projects will be able to connect to the network sooner than under the existing arrangements. | Positive impact on our ability to serve for our customers and connect them in a timely manner. However, radical change to the new arrangements will be a large transition for the business and Customer Connections. | Following 'go ahead' from the CDB on 21 March, ESO will start the next phase of proposing implementation of their reform recommendations. This is likely to be through a suite of urgent code modifications, which we will support development of. Their objective is to have reform implemented ready for 'go live' by January 2025. | Urgency is required due to the current connections landscape.
Coordination and cooperation activity | NGED/0058 | NGET/0042 | ENA, ESO | All DNOs, TOs and ENA | Reform of the technical Limits in the GB Connections arrangements that are specific to our interaction with the DNOs | In progress | ENA/ESO/NGET/DNOs produced a Technical Limits Rulebook in 2023. The implementation of GSP Technical Limits at 70+ Grid Supply Points across England & Wales. The implementation of Technical Limits at a further 70+ GSPs is taking place in Q2/Q3 2024. | 2023-06-01 | This will impact how generation customers can connect at a Distribution level | N/A | N/A | N/A | Positive impact on customers and their connection timescales. Those progressing their projects will be able to connect to the network sooner than under the existing arrangements. | Positive impact on all involved and NGETs ability to connect customers to the system quicker. | Continue implementation of technical limits. | N/A as recommendation already in progress
Coordination and cooperation activity | NGED/0059 | NGET/0043 | ENA, ESO | All DNOs, TOs and ENA | Introduction of Distribution Forecast Transmission Capacity allowing DNOs to speed up the connection application/assessment process for embedded generation | In progress | ENA/ESO/NGET/DNOs are currently producing a detailed technical report capturing what DTFC is and the benefits it will bring. This will then be translated into a Rulebook along with only code modifications needed for CUSC or D-Codes. | 2023-11-01 | This will impact how generation customers can connect at a Distribution level | N/A | N/A | N/A | Positive impact on distribution customers and their timescales for receiving offers from DNOs as they will be better informed by Transmission Network constraints. | Positive impact on all involved and will help ET optimally plan the network more efficiently. | ENA SCG to draw up more detailed proposal for how DNOs will forecast required capacity, how it will be assessed by TOs and how it will be returned and approved by TOs/ESO. | Recommendation to explore this further to help support development of this solution.
Coordination and cooperation activity | NGED/0012 | NIA | ESO, NGED | ESO, NGED | On a yearly basis NGED hold detailed bilateral discussions with ESO to discuss FES/DFES interaction and data sharing opportunities. | as BaU | Annual Process | 2018-11-30 | This interaction allows for discussion on forecasting data and assumptions specifically related to NGED licence areas. This discuss helps to ensure a Whole System approach is taken to forecasting and that the DFES bottom-up approach aligns with the FES top-down methodology. |  |  |  | Coordinated long-term forecasting between electricity networks, stakeholder benefit of consistency when comparing scenario projections of different networks. | Continual improvement and alignment of top-down and bottom-up scenario forecasting approaches. | Annual process | To produce annual scenario forecasts for distribution network planning.
Related action | NGED/0012/A01 | NIA | NGED | [13 empty] | Following regular discussion with the ESO related to the Future Energy Scenario (FES) interaction, NGED now share key DFES data with the ESO to ensure better Whole Electricity System alignment | 2019 | Mature | NGED/0012
Related action | NGED/0014/A01 | NIA | NGED | [13 empty] | Reviewed internal processes for producing CIM models and compliance with GC0139. This will help NGED customers and stakeholders as it will provide critical network data in a standardised format that will help facilitate Whole System outcomes and open data sharing. | 2023-11-01 | Improving | NGED/0014
Coordination and cooperation activity | NGED/0023 | NIA | NGED | NGED, ESO, SPEN, SSEN, UKPN , NPG | Agree and co-ordinate outages across boundaries. | as BaU | Ongoing | Ongoing | This is an opportunity to agree running and operating regimes under system abnormal conditions to maximise system security (e.g. running arrangements for a maintenance outage). |  | Loading data is provided by each party alongside a selection of running arrangements that would restrict the other parties work scheme. This is restricted sharing between parties. |  | Positive - this data sharing acts as an interface to maximise system security and coordination under normal day-to-day operations (e.g. maintenance outages). | Positive - this data sharing acts as an interface to maximise system security and coordination under normal day-to-day operations (e.g. maintenance outages). | Ongoing | License condition
Coordination and cooperation activity | NGED/0024 | NIA | NGED | NGED, ESO, SPEN, SSEN, UKPN , NPG | Real time control and operation of the network. | as BaU | Ongoing | Ongoing | Real time control and operation of the network to facilitate works on assets across boundaries. |  | We share data of how the network is running across boundaries, agree operational instructions and share switching programmes and loadings. This is restricted sharing between parties. |  | Positive interaction to maintain the security and stability of the network. This level of coordination and collaboration helps facilitate works undertaken on each network. | Positive interaction to maintain the security and stability of the network. This level of coordination and collaboration helps facilitate works undertaken on each network. | Ongoing | Operational running requirements
Coordination and cooperation activity | NGED/0026 | NIA | ESO | NGED | Virtual Energy System seeks to streamline the sharing of modelling data across different licensee's. | In progress | Innovation Project Registered in March 2022 | 2022-03-01 | Aims to provide efficiencies through enhanced coordination of network planning and real-time operation. | https://www.nationalgrideso.com/virtual-energy-system | Data within the discovery phase of the SIF project was shared between project partners. |  | Building on week 24/42 data exchange between DNO and ESO. As detailed in NGED/0013, NGED/0014 and NGED/0015. | Positive impact as it will increase the granularity, frequency and exchange format that data is shared between DNOs and ESO/NGET. This may also benefit wider stakeholders and energy vectors. | In discovery phase | Continue reviewing and ensure alignment with Grid Code 0139 changes
Coordination and cooperation activity | NGED/0027 | NIA | Wales and West Utilities | NGED, Octopus Energy, SSEN, SPEN | HYPARK a partnership with Wales and West Utilities, Passive UK, Octopus Energy, SSEN, SPEN & Easee. The project makes use of the unique benefits of stationary gas-grid (Inc. hydrogen) connected fuel cell technology to deliver a GB-first on-site electricity generation for EV charging. | In progress | Innovation Project Registered in March 2022 | 2022-03-01 | By applying optimisation software it could offer balancing services (grid capacity/flexibility) while fulfilling EV charging requirements in condensed cities and towns. | SIF_WWU_2_01 (energynetworks.org) | Data within the discovery phase of the SIF project was shared between project partners. |  | Positive as by applying optimisation software it could offer balancing services (grid capacity/flexibility) while fulfilling EV charging requirements in condensed cities and towns. |  | In discovery phase | Continue progressing Innovation project
Coordination and cooperation activity | NGED/0028 | NIA | ESO | NGED, SSEN ,Octopus Energy, Centre for Net Zero and Ohme | Crowdflex seeks to characterise domestic flexibility for use in grid operations. | In progress | Innovation Project Registered in March 2022 | 2022-03-01 | This will be with a view to informing this statistical view of domestic flexibility, providing key data packages for new grid models, and informing greater use in market operations. | Regular meeting | Data within the discovery phase of the Strategic Investment Fund (SIF) project was shared between project partners. |  | Positive collaboration to improve understanding across the Whole Electricity System on the benefits and impact of domestic flexibility. | Through better understanding of the potential of domestic flexibility the best Whole System solution can be utilised, particularly around the balance between conventional reinforcement and flexibility procurement. | In discovery phase | Continue discovery phase of Innovation project
Coordination and cooperation activity | NGED/0029 | NIA | NGED | Octopus, SP Energy, Welsh Government and West Midlands Combined Authority Stakeholders include ESO | Project Equinox seeks to make Whole System integration of heat pumps easier, This is by developing a combined flexibility proposition from Suppliers and DNO's to heat pump owners. | In progress | Innovation Project NIC competition winner in 2021. Trials are now underway. | 2022-03-01 | Equinox has suppliers and DNO's working together to provide a combined flexibility incentive to customers with heat pumps. | https://www.westernpower.co.uk/innovation/projects/equinox-equitable-novel-flexibility-exchange | Project data will be shared between licensees to enable design of the flexibility product. |  | Positive collaboration to improve understanding across the Whole Electricity System on the benefits and impact of heat pump flexibility. | Through better understanding of the heat pump flexibility the best Whole System solution can be utilised, particularly around the balance between conventional reinforcement and flexibility procurement. | Project has just mobilised | Continue with NIC project to better understand key outcomes of Whole System heat pump integration.
Coordination and cooperation activity | NGED/0030 | NIA | NGED | WWU, West of England Combined Authority (WECA) | Energy Planning Integrated with Councils (EPIC) is an NIA funded Innovation project looking to create a standardised process for creating local authority energy plans and ensuring the plans are captured in the Distribution Future Energy Scenarios (DFES). | Complete | NIA Innovation Project | 01/02/20221 | Ensuring that local authority energy plans are accurately captured as part of the DFES process is at the heart of coordinated Whole System planning. These plans are inherently cross energy vectors, so accurately reflecting this data in the DFES will benefit all energy vectors. It is also one of the first time the ENA WS4 Product 1 Whole System CBA tool has been tested and fed back to the working group. | https://www.westernpower.co.uk/projects/energy-planning-integrated-with-councils-epic | Sharing of regional gas scenarios by WWU and WPD Best View data. There will also be data sharing with local authorities as part of three trial areas to generate local energy plans. Learning from use of the Whole System CBA tool has also been fed back to the ENA working group. | https://www.westernpower.co.uk/projects/energy-planning-integrated-with-councils-epic | Standardising the process for creating local energy plans with gas and electricity will improve the Whole System integration with gas and electricity. It will help develop tools that can plan investments on the gas and electricity network, better accounting for the needs of local authority and identifying potential synergies. | Improve existing DFES process so synergies are captured between local authority energy plans and better aligned with development of electricity and gas network strategic planning. Part of this project is also looking at analysing HV and LV networks to determine network and non-network solutions. This will help better inform WPD's approach to conventional vs flexibility procurement to ensure the best long-term value to the customer is provided. | Ongoing | Convert any learning from this project into business as usual.
Coordination and cooperation activity | NGED/0031 | NIA | NGED | All DNOs, GDNs, GT and ET | National Energy System Map, providing high-level linear asset geographic information in a single location | Complete | Published online | 2021-06-01 | Enables a consolidated G and E view of assets to inform operations and investments |  | Open data - linear asset geographic information |  | Positive through greater and consolidated data access in a visualised manner. | Reduced requirement to share data in a piecemeal fashion. | Implement learning from project
Coordination and cooperation activity | NGED/0032 | NIA | NGED | Energy Systems Catapult (ESC) | Data Science Challenges | Complete | Published online | 2021-12-01 | Creates a space and value from NGED and other energy data to drive insight against a set of specific use cases. | https://www.westernpower.co.uk/news-and-events/latest-news/were-launching-a-new-data-science-competition | Multiple datasets to drive data science activity as well as repositories of shared insight following completion of challenges | https://github.com/NGED-data | Creating an environment across UK energy sector to drive value from data to meet current and future Whole System challenges. | Demonstrated the openness and availability of data to benefit | Continue with data challenges and progress ideas from challenges
Coordination and cooperation activity | NGED/0033 | NIA | NGED | SPEN, SSEN, NPG | Flexible Power collaboration | In progress | Ongoing | 2020-10-01 | Collaborative development of the Flexible Power website and portal to align customer journeys for flexibility service provision | https://www.flexiblepower.co.uk/ |  |  | The provision of a common interface for the provision of Flexibility Services | A common approach to Flexibility Services. Cost sharing for development work. | Ongoing | Continue to provide the tools needed.
Coordination and cooperation activity | NGED/0034 | NIA | NGED, ESO | NGED, ESO | MW Dispatch Regional Development Programme (RDP) | In progress | Ongoing | 2018-01-01 | Development of a coordinated service for the deployment of Connect and Manage Principles on the Distribution Network. This allows Distribution Energy resource (DER) to connect to the network and be actively managed, rather than triggering wider Transmission works. | https://www.nationalgrideso.com/research-publications/regional-development-programmes | We are establishing data sharing processes to facilitate service registration, the management of asset unavailability, real time metering and dispatch. |  | The connection of more DER in the South West, without triggering wider Transmission works. This allows DER to connect faster, and the costs to be deferred. | Additional Capacity available to DER | Ongoing | ongoing development of MW Dispatch product and supporting systems.
Coordination and cooperation activity | NGED/0035 | NIA | NGED, ESO | NGED, ESO | Connecting Storage in the Midlands Regional Development Programme (RDP) | Complete | Complete | 2019-01-01 | Development of a coordinated approach to manage the connection of new storage sites and their impact on the transmission network. | https://www.nationalgrideso.com/research-publications/regional-development-programmes |  |  | The connection of more storage sites, that can the provide services to the system. | Additional Capacity available to Storage sites. | Close | Work on the RDP was completed. Some of the thinking was fed into the wider T/D boundary work.
Coordination and cooperation activity | NGED/0038 | NIA | NPgY, NGED | NPgY, NGED | As required planning & co-ordination meeting | as BaU | Initial meeting completed in 21/22 with a long term aspiration to establish a formal interaction with a Distribution licensee who is adjacent to the NPg licence area. | 2021-09-01 | The meeting is a formal interaction between two adjacent distribution licence holders to identify and monitor existing and/or future Distribution network interfaces. |  |  |  | The activity is an essential and timely review of ongoing relationship between all parties. The meeting has a positive impact as it provides a forum for Whole Electrical System discussions and collaborations. | The activity has a positive impact on the activity of the licensee. | Continue the meeting every six to twelve months (dependent on level of interaction required). | License condition. The meeting is essential to ensure the continued and efficient interaction between all parties.
Coordination and cooperation activity | NGED/0039 | NIA | ENA | NGED, All DNOs and ESO | Development and implementation of Primacy rules for service conflict between ESO and DNO services. This is a subset of NGED/0003 | In progress | Some rules have been deployed. The focus is now on data exchanges to scale up the coordination | 2021-07-01 | This activity looks to manage the potential conflict between ESO and DNO services | https://www.energynetworks.org/industry-hub/resource-library/on-primacy-rules-for-eso/dno-coordination-ver-1.0-(mar-2023).pdf | Depends on the use cases. This is covered in individual sign off sheets |  | This will enhance the coordination between ESO and DNO services and reduce conflict | Increased data sharing requirements to support rules | Continue | This is a key coordination activity within the Open Networks project
Related action | NGED/0039/A01 | NIA | ENA | NGED, All DNOs and ESO | [12 empty] | Implementation of Primacy rules for DNO services and the BM | 2023-04-01 | BaU | NGED/0039
Coordination and cooperation activity | NGED/0042 | NIA | DCUSA | All DNO's and some IDNO's | DCUSA change proposal brought forward from Ofgem's Forward Looking and Access Significant Code Review. Introduction of new non-firm (curtailable) access rights for distribution connected users. | Complete |  | 2022-12-01 | Ensuring that all customers experience the same level of access rights and connection charges across all DNO's and IDNO's. |  |  |  | Changes made to DCUSA and to the Common Connection Charging Methodology between DNO's | Helps to enable connections onto the network
Coordination and cooperation activity | NGED/0043 | NIA | DCUSA | All DNO's and some IDNO's | DCUSA change proposal brought forward from Ofgem's Forward Looking and Access Significant Code Review. Implement the outcomes of Ofgem’s Access and Forward-Looking SCR in respect of curtailable connections where the customer is connected to a different licenced DNO than the network that drives the requirement to curtail the customer | Complete |  | 2022-12-01 | Ensuring that all customers experience the same level of access rights and connection charges across all DNO's and IDNO's. |  |  |  | Changes made to DCUSA and to the Common Connection Charging Methodology between DNO's | Helps to enable connections onto the network
Coordination and cooperation activity | NGED/0044 | NIA | DCUSA | All DNO's and some IDNO's | DCUSA change proposal brought forward from Ofgem's Forward Looking and Access Significant Code Review. | Complete |  | 2022-12-01 | Ensuring that all customers experience the same level of access rights and connection charges across all DNO's and IDNO's. |  |  |  | Changes made to DCUSA and to the Common Connection Charging Methodology between DNO's | Helps to enable connections onto the network
Coordination and cooperation activity | NGED/0045 | NIA | DCUSA | All DNO's and some IDNO's | DCUSA change proposal brought forward from Ofgem's Forward Looking and Access Significant Code Review. Definition of Demand and Generation connections; Reflecting terms throughout Schedule 22 (the CCCM) of the DCUSA. | Complete |  | 2022-12-01 | Ensuring that all customers experience the same level of access rights and connection charges across all DNO's and IDNO's. |  |  |  | Changes made to DCUSA and to the Common Connection Charging Methodology between DNO's | Helps to enable connections onto the network
Coordination and cooperation activity | NGED/0020 | NGET/0058 | DESNZ | DESNZ, all DNOs, all GDNs, TOs | DESNZ Heat Infrastructure Transformation project - Cost analysis of electrification of heat out to 2050 to be compared to hydrogen alternative | In Progress | Discussions ongoing to define scope ahead of analysis kick off | 45266 | Cost analysis of electrification of heat out to 2050 to be compared to hydrogen alternative. Analysis o be carried out across gas networks and electricity networks and CBA done. |  | None yet beyond calls discussing options for methodologies. |  | Input for government decision on hydrogen for heating 2026. | Positive as the decision on hydrogen for heating will provide direction and reduce uncertainty in forecasting. | Continue engagement and contribute to analysis needs. | analysis on the electricity network is crucial to make an informed decision due to the impacts of hydrogen for heating decision on heat electrification.
Coordination and cooperation activity | NGED/0019 | NIA | NGED | all DNOs, ENA | Open networks forum - Common Evaluation Methodology (CEM) tool (Workstream 1A) | In Progress | BaU meetings to discuss development and maintenance of CEM tool used for assessment of investment pathways (specifically conventional reinforcement against flexibility as part of the Distribution Network Options Assessment process). | 44197 | Coordination across DNOs to ensure consistency |  | no data shared, input provided on statements and views. |  | positive, coordinates DNOs to give consistent messaging on forecasting topics such as FES usage | Positive, ensures NGED can contribute to position statements and discussions | Continue engagement | ensuring that NGED's views continue to be represented in the DNO statements and discussion with Ofgem and ESO.
Coordination and cooperation activity | N/A | NGET/0004 | ESO | ESO, NGET, SPT & SSEN | The Offshore Coordination Project and Holistic Network Design is looking at how the ambition to connect 40GW of Offshore Wind and ScotWind projects can be accommodated by 2030. The project is coordinated by the ESO and involves all of the TOs in Great Britain. |  | The "Pathway to 2030 Holistic Network Design" was published July 2022 | 2022-02-01 | Holistic Network Design is to consider a design for the 2030 network to accommodate 40GW of wind | https://www.nationalgrideso.com/future-energy/pathway-2030-holistic-network-design | N/A | N/A | This project is being developed to understand the most effective approach to developing 40GW of offshore wind and ScotWind | This will ensure that NGET and other TOs within Great Britain can accommodate offshore renewable wind in the most effective way | Publication by ESO of the output from the working group was done in July 2022, and "The Holistic Network Design Follow-up Exercise (HNDFUE)" was started to consider the outcomes of the HND carefully when determining the follow-up design. | This work will help inform connection of offshore wind critical to delivering Net Zero.
Coordination and cooperation activity | N/A | NGET/0006 | ESO | ESO, NGET and Suppliers | National Grid is providing counterfactual information and assessing stability solutions for ESO Pathfinder Projects. | In progress | Providing counterfactual and participating in pathfinder solutions | 2020-05-01 | Pathfinders are developed to maintain transmission system operability and stability | https://www.nationalgrideso.com/future-energy/projects/pathfinders | N/A | N/A | Counterfactual and solutions provided by NGET will enable the selection of the best solution for pathfinder projects including from competitive suppliers. | This will provide a positive impact in the holistic system stability and operation | ESO to consider pathfinder information to select applicable solutions | NGET support the ESO pathfinder process.
Coordination and cooperation activity | N/A | NGET/0008 | NGET | UKPN, Offshore and Onshore Generators/Interconnectors | East Anglia is seeing a large increase in connections to renewable generation and interconnectors. NGET is working closely with all stakeholders to ensure infrastructure can be combined in the best Whole System approach. This includes Bramford to Twinstead project where NGET is proposing to use UKPN route corridors and providing UKPN with replacement capacity to minimise impact of new infrastructure. Also Sealink project where we are coordinating with generation and interconnectors. | In progress | Ongoing appraisal of infrastructure impacts and whole system contribution. These projects are now part of the Accelerated Strategic Transmission Investment (ASTI) projects SeaLink project is finalising the options following consultation, ready for submitting the Development Consent Order. | 2012-08-01 | Consideration of the Whole system impacts across East Anglia and developing the Whole System solutions that deliver the best value inline with our obligations. | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/bramford-twinstead https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/norwich-to-tilbury https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/sealink/about-sea-link https://www.ofgem.gov.uk/publications/decision-accelerating-onshore-electricity-transmission-investment | N/A | N/A | This will enable the connection of renewable and net zero generation, along with interconnections to Europe, Providing Whole System Solutions in the support of Net Zero. | This is appropriate approach to ensure infrastructure delivers the best Whole System solution across the Whole Electricity System. | Continued development of infrastructure solutions coordinating across generation and networks. | The infrastructure is required to deliver Net Zero and our obligations drive us to achieve effective Whole System Solutions.
Coordination and cooperation activity | N/A | NGET/0010 | NGET | UKPN | NGET is working on network updating in South East and London area. NGET has been working with UKPN on the London Power Tunnels Projects to provide Whole System Solutions for demand growth across London and reduction in disruption by rewiring London in tunnels rather than road laid cables. | In progress | Phase 1 was completed in 2018 with further stages in construction due for completion 2027. | 2009-08-04 | This work is coordinated across transmission and distribution to keep London connected and allow demand growth delivering Net Zero. | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/london-power-tunnels-project https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/grain-to-tilbury https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/north-london-reinforcement | N/A | N/A | This enables growth of Demand in London and establishes network capability across the Whole Electricity system in support of delivering Net Zero. | This is appropriate approach to ensure infrastructure delivers the best Whole System solution across the Whole Electricity System | Continued delivery of the project | The infrastructure is required to deliver Net Zero and our obligations drive us to achieve effective Whole System Solutions.
Coordination and cooperation activity | N/A | NGET/0011 | NGET, SSEN & SPT | NGET, SSEN & SPT | NGET, SSEN & SPT are developing HVDC connections on the East Coast known as E2DC (NOA) Torness- Hawthorne Pit, E4D3 (NOA) Peterhead to Drax. All three Transmission Owners are working together to develop an agreed technical solution for these links before the projects separate out into separate entities | In progress | Eastern Link 1 is nearing the end of the development phase, construction work is planned to commence in 2025, with the new connection anticipated to be operational in 2029. Eastern Link 2 is in the development phase, construction work is planned to commence in 2024 with the new connection due to be operational in 2029. These projects are now part of the Accelerated Strategic Transmission Investment (ASTI) projects. | 2020-03-01 | By working together all tree TOs can apply standard technical solution that works holistically across GB. This will benefit future projects and reduce costs of specifying two projects independently. | https://www.easterngreenlink1.co.uk/ https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/segl2 https://www.ofgem.gov.uk/publications/decision-accelerating-onshore-electricity-transmission-investment | N/A | N/A | These connections enable the increase of capacity between Scotland and England increasing the flow of renewable energy. By working together to achieve standard solutions across projects delivers efficiencies for consumers | This is appropriate approach to ensure infrastructure delivers the best Whole System solution across the Whole Electricity System | Use standard approach for future projects | Coordinated efficiencies benefit Whole System approach and further opportunities to minimise resources benefiting consumers.
Coordination and cooperation activity | N/A | NGET/0013 | NGET | SSE Energy Solutions | Development of Holistic Waste Heat Recovery from transmission assets | In progress | Innovation Project | 2021-11-01 | Evaluate the potential technical barriers to recovery of heat from transformers for a district heat scheme for homes/businesses | https://smarter.energynetworks.org/projects/nia2_nget0003/ | Mutual NDA in place between NGET and stakeholder. NGET shared load/transformer data. Stakeholder shared heat exchanger design. | N/A | The project will look at the technical feasibility of capturing heat (from losses) from transformers to determine whether this can be done economically for external heat networks. The impact of different control schemes on the transformer life will also be considered. | if it is economically possible to recover heat from assets it will be positive use of energy normally unused. | Innovation project to establish the technical requirements and solutions which would feed into an economic assessment. | Innovation project will establish if solutions offer benefit.
Coordination and cooperation activity | N/A | NGET/0014 | NGET | NGET, NGG, ESO | Project to consider Gas and Electricity infrastructure outlook in 2050. Considering how infrastructure asset utilisation can be maximised through location of hydrogen electrolysis, electricity and gas infrastructure. | Complete | Innovation Project | 2022-01-27 | can Hydrogen assets facilitate greater utilisation of electricity assets through strategic locations. | https://smarter.energynetworks.org/projects/nia_nggt0184/ | N/A | N/A | Could increase utilisation of transmission network and expand electricity generation market across the day and seasons. | greater utilisation of transmission network providing benefits to electricity market and hydrogen production | Project has reached a conclusion: Across all the modelled scenarios integrated electricity and hydrogen transmission infrastructure planning can realise savings. Early investments common across the transmission networks are needed to realise these savings. | Please see report on website for the justification of conclusion
Coordination and cooperation activity | N/A | NGET/0015 | NGET | NGET, SSEN & SPT | The Transmission Owner Tools for EMT Modelling (TOTEM) project is developing new network modelling tools that can better determine system control and stability in our changing network. | Complete | Innovation Project | 2021-07-27 | as the network develops the dynamics are changing, all transmission network operators and owners need to understand the effects to keep the Whole Electricity system stable going forward | https://smarter.energynetworks.org/projects/nia_shet_0032 | N/A | N/A | A new system will allow all transmission owners and operators to understand the changing electricity system as we approach Net Zero | the innovation project will identify new suppliers of network models for transmission owners and operators to use to develop Whole System solutions for 2050 and beyond. | Complete | Please see report on website for the justification of conclusion
Coordination and cooperation activity | N/A | NGET/0017 | NGET | NGET, ENW & SPT | Harker Substation located near to Carlisle in the North West of England. A significant number amount of generation is seeking connection into ENW and SPT networks and working across the three networks we are identifying the right Whole System solution to accommodate all the connections. | In progress | SPT | 2018-12-28 | Considered and defined whole system solutions across networks. | https://www.nationalgrid.com/electricity-transmission/infrastructure-projects/harker-substation | N/A | N/A | This will ensure the best solution is selected to give the effective Whole System solution. | It allows DNOs to connect more existing customers to their networks, and allows extra capacity for future connections. | Site construction work commencement in 2024. | In order to meet the customer expectations on DNO's network capacity.
Coordination and cooperation activity | N/A | NGET/0019 | NGET | NGET, NGG, Arup and University of Manchester | NGET is producing a Resilience Framework and Model that measures our resilience and interdependencies. This will help identify the Whole System solutions required to deliver a resilient infrastructure system fit for 2050. | Complete | framework has been developed NGET establishing how we implement as BAU | 2020-01-01 | resilience is very important in the understanding of Whole System infrastructure | N/A | N/A | N/A | The resilience framework will help identify shortfalls introduced during our transition to Net Zero | Positive impact of making Net Zero transition resilient. | deliver Resilience Framework to BAU | Deliver resilience into the Whole Electricity system solutions and ownership
Related action | N/A | NGET/0019/A001 | NGET | NGET | [12 empty] | Resilience Framework was developed and has since been worked on to be more widely applicable to the energy sector and Critical Network Infrastructure (CNI). Now complete, and has been groupwide deployed and tested in 2023. It will conclude in May 2024. The output will be used to inform business strategies. Group Resilience has engaged and is continuing engaging with external stakeholders (Ofgem, DESNEZ, Cabinet Office, etc) to share relevant information e.g. lessons learnt etc. | Launched in Q2 2023. | BaU | NGET/0019
Coordination and cooperation activity | N/A | NGET/0021 | NGET | SPEN, SSEN,ESO | The project is to develop a co-simulation approach which will reduce the modelling efforts and improve the efficiency of the simulation on system dynamic analysis for large networks. It will also improve the accuracy of the modelling and reduce the risk in planning and design. | In progress | Innovation Project | 2022-02-01 | The dynamics of the network develops are changing with high penetration of power electronic interfaced devices. Efficient modelling approach is required for all transmission network operators and owners to efficiently capture the characteristics of the dynamics of the network for planning and operation to ensure the security of the Whole Electricity system in the transition to net zero. | https://smarter.energynetworks.org/projects/nia2_nget0020/ | N/A | N/A | A new simulation approach will allow all transmission owners and operator for a more efficiency and accurate modelling approach which will help to reduce risk in planning and operation. | If this innovative modelling approach is successful, it will bring benefits to system planning, customer connections and network operation during the transition to NetZero. | Continue working on the project. | The innovation project will establish the economics of the considered options.
Coordination and cooperation activity | N/A | NGET/0022 | NGET | NGT | This project aims to analyse the benefits of linking electricity and hydrogen vectors from a whole-system perspective to determine the optimum capacity, location, technologies, and system benefits of electrolysers under different future development scenarios. | In progress | Innovation Project | 2022-06-01 | The impact of power-to-gas on the whole energy system | https://smarter.energynetworks.org/projects/nia2_nget0002/ | N/A | N/A | Analyse the benefits of linking electricity and hydrogen vectors from a whole-system perspective to determine the optimum capacity, location, technologies, and system benefits of electrolysers under different future development scenarios. | The project will develop an integrated whole system model to optimise the portfolio and locations of electrolysers considering several factors such as system constraints, end-use application of hydrogen, hydrogen transportation costs to end-use, and water availability to provide cost effective investments to achieve decarbonization of energy networks. | Innovation project continue to develop analysis | The innovation project will establish the economics of the considered options.
Coordination and cooperation activity | N/A | NGET/0023 | NGET | NGT | This project will define technology-based, temporal, and geospatial water constraints to 2050, then use whole energy systems modelling to analyse how these projections (and associated uncertainties) could impact the least cost energy system design. | In progress | Innovation Project | 2023-03-01 | How water constraints could impact the electricity system | https://smarter.energynetworks.org/projects/nia2_nget0026/ | N/A | N/A | It will produce knowledge and a model to identify the impact of water constraints on energy systems. | By representing joint probability stress events across the two sectors, this project will also use a Power Factory-based approach to quantify operational constraints faced by the electricity transmission network. | Continue working on the project | The innovation project will establish the economics of the considered options.
Coordination and cooperation activity | N/A | NGET/0024 | ESO | ESO, NGET, SPT & SSEN | The Offshore Coordination Project and Holistic Network Design is looking at how the ambition to connect 50GW of Offshore Wind and ScotWind projects can be accommodated by 2030. The project is coordinated by the ESO and involves all of the TOs in Great Britain. Work has now commenced on the Holistic Network Design Follow up Exercise (HNDFUE), which is the phase 3. | In progress | Weekly Group Meetings are Ongoing |  | This HND follow-up exercise (HNDFUE) will further support the Government's previously stated government targets for offshore wind and net zero; facilitating an economic, efficient, operable, and coordinated National Electricity Transmission System (NETS) (including offshore and associated onshore assets required to connect in scope projects). | https://www.nationalgrideso.com/document/270851/download | N/A | N/A | The phase 3 of this project is being developed to understand the most effective approach to developing and connecting 50GW of offshore wind and ScotWind | This will ensure that NGET and other TOs within Great Britain can accommodate offshore renewable wind in the most effective way | Publication by ESO of the output from the working group expected in July 2023 March 2024 | This work will help inform connection of offshore wind critical to delivering Net Zero.
Coordination and cooperation activity | N/A | NGET/0025 | ESO | All TOs, OFGEM | TEC (Transmission Entry Capacity) Amnesty. | Complete | Completed. Ofgem has approved Code Modification CMP376 – Inclusion of Queue Management process within the Connection and Use of System Code (CUSC). |  | TEC amnesty will help to reprioritise connections to the NETS by implementing a more effective Queue Management (QM) arrangements. It will improve the queue management and deliver value to consumers by better optimising the investments required to connect Customers, as well as helping deliver Government’s decarbonisation policies. | https://www.nationalgrideso.com/industry-information/connections/our-five-point-plan#:~:text=The%20TEC%20amnesty%20is%20now,projects%20applied%20to%20terminated%20contract.&text=On%2022%20September%202022%20the,a%20reduced%20or%20no%20cost. https://www.nationalgrideso.com/industry-information/connections/tec-amnesty | N/A | N/A | Ensure network capacity allocated to developers is fully utilised. Network investment to facilitate User connections remains economic and efficient. | Improves current connection process and waiting time | ESO to continue work to improve the connections process. | The next stage activity is as was the original plan.
Coordination and cooperation activity | N/A | NGET/0026 | NGET | ESO/Ofgem/DESNZ/NTCA/Port of Tyne/Local Tyne Businesses/Local MP | B7 Tyne River OHL Crossing Project. It is a proposal to divert OHL using underground cable, this will allow Tyne business to continue using the river for tall structures, to conduct the industrial business. | In progress | Feasibility Assessment Pre-Gate A2. | 2022-07-01 | Removal of OHL eliminates obstruction to businesses on Tyne. It can create up to £800m of GVA for UK tax payer and 1800 new jobs for the region. | N/A | Business case benefits shared with DESNZ and Ofgem | N/A | UK Plc & Electricity Consumer benefits through constraint cost avoidance and Net Zero plan conflict. | Reduced levels of Opex related to planned outages and align with National Grid values. | Confirm funding route via ministerial decision with DESNZ and Ofgem. | Government departments have been provided all the data in order to make the political decision on funding.
Coordination and cooperation activity | N/A | NGET/0029 | NGET | ENW | Manchester long term optimisation planning. | Complete | Analysis complete, results shared with ENW. | 2019-08-01 | Proof of concept for joint Tx and UHV Dx regional whole system planning and optimisation to 2050 | N/A | Output of activity including designs and conclusions shared with ENW and other DNOs through NGET-DNO workshops | N/A | Proof of significant benefit of co-optimisation of Tx and UHV Dx planning to meet demand growth required for a Net Zero 2050 Manchester. Benefits are in deliverability, societal impact and cost. | Created first iteration of process and tools for 2050 long term whole system planning. | Continue to improve process and tools, engage with DNOs and test in other areas. See NGET/0027 and NGET/0028. | This case study showed significant potential benefits of this approach.
Coordination and cooperation activity | N/A | NGET/0035 | SSEN-T | NGET, SGN, Icebreaker one, Olsights, MapStand | REACT (Rapid Evaluation Areal Connection Tool) aims to create a geographical planning tool providing users with the ability to view electricity gris connection requests in real-time using an interactive visualisation map. | In progress | Partners have created the tool and it is getting updated considering the feedback from different users. | 2023-10-01 | The tool will be available to developers, system planners, and other users in the pre-application stages | https://smarter.energynetworks.org/projects/ukri10058535/ | N/A |  | A new tool to ease the pre-connection application and stakeholders will be evaluate themselves | It will make the evaluation process easier for utilities | More feedback is necessary form the different user groups | Developers used their experiences to create the tool but the usability will depend on the feedback from users and recommendation from the advisory group.
Coordination and cooperation activity | N/A | NGET/0039 | EPN,LPN,SPN | ESO, NGET | Transmission - Distribution outage coordination via common working practises and common functions. Enhancement of current process which are Grid Code requirements under OC2 which mandate at three periods in the year ESO must provide outage plans to the DNOs. The DNOs collaborate in the creation and agreement of these plans. There are bi monthly and weekly TO, ESO, UKPN Outage Planning meetings/calls for outage coordination and then ad-hoc discussions as required. | In progress | ESO have commenced work with DNOs - Deeper Access Planning Project | 2023-12-01 | UKPN and NGET are able to make coordinated decisions on outage plans which drives the best end consumer benefit. | N/A | N/A | N/A | Leads to more efficient use of services across transmission and distribution. Leads to better decision making on outage plans and hence delivery of more work on both sides. | Generally positive impact on NGET's ability to plan current year outages and urgent requests which impact on UKPN. | Continue workgroup meetings | Regular plan reviews support our outage planning and decision making process
Coordination and cooperation activity | N/A | NGET/0040 | ESO | DNOs, NGET, ESO | Joint System Design Liaison Meeting (JSDL). Topics of discussion include and not limited to: GSP BO7 Compliance Review - Forecasted Demand Growth reports System Planning System Design Asset Replacement Plans | In progress | Bi-Annual occurrence with each relevant DNO license area across England and Wales. Outputs include reviewing proposed local Transmission Reinforcement Works at the Transmission and Distribution interface. | 2010-01-01 | Provides impetus for whole system planning and for the TO and DNO to share their upcoming RIIO / ED plans. | N/A | N/A | N/A | Positive impact on customers. Encourages TO and DNO to work towards the most Economic and Efficient solution to connect customers to the Grid in a timely manner. | Positive impact on TO's investment plans ensuring that the TO is Economic and Efficient. | JSDL meetings to continue and evolve with the Connections Landscape. | JSDL Meeting is underwritten within the STC as necessary vessel for whole system planning between TO, SO & DNO.
Coordination and cooperation activity | N/A | NGET/0055 | SEPD | NGESO, NGET, GLA, UKPN | Long term transmission investment in the GLA area, covering six GSPs, had the potential to reduce customers ability to connect to the distribution network. This collaborative project (West London Electrical Capacity Constraints) aimed to remove barriers for connections, review contracted queue management and determine material thresholds for each GSP. | In progress | SSEN Distribution have introduced a new process as a trial for customers connecting to the GSPs within the GLA area. This will offer customers the ability to stage their connection; connecting within the materiality threshold each year. We are now looking to use this process more widely across our licence areas. In addition we have also developed flexibility services to release additional capacity in the areas. | 2022-07-01 | This work combines extensive stakeholder engagement with the GLA, NGESO & NGET. SSEN Distribution have also put forward a process to the ENA for approval with all other DNOs. | https://www.london.gov.uk/sites/default/files/checked_westlondoncapacity_0.pdf | N/A | N/A | The process is enabling customers to connect to the network ahead of wider transmission reinforcement and is improving data sharing to inform future investments. | Positive impact that demonstrates that through successful stakeholder engagement, distribution and transmission businesses are able to work collaboratively to remove connection barriers. | On-going monthly meetings with GLA, SSEN and NGESO to ensure that we proactively progress the proposals and are prepared for any future concerns that may arise. | Continued data and knowledge sharing will improve working relationships, enhance collaborative approaches, drive efficient working practices and enable all parties to evidence future investment requirements.
Coordination and cooperation activity | N/A | NGET/0056 | SEPD | NGET & ESO | SSEN and ESO are working on multiple Regional development programmes (RDPs) and TD boundary ANM systems set up to meet new contractual requirements between National Grid Electricity Transmission (NGET) and SEPD. These RDPs and TD boundary ANM systems were introduced because the amount of Distributed Energy Resources connected, and connecting to the distribution networks was believed by National Grid ESO to be impacting the transmission network. Examples include South West Active Network Management (SWAN) and Minety GSP. | In progress | Minety is operationally live as of 10/2023. SWAN is now operationally live as of March 2024. | 2017-01-01 | Collaboration across electricity transmission and distribution licensees allows for more customers to connect to the distribution network ahead of transmission related reinforcement. | https://www.ssen.co.uk/our-services/swans/ | N/A | N/A | Efficiently maximises benefit from the existing distribution system and reduces the need for a traditional asset augmentation/investment type approach. Provides early access for customers to distribution networks. | Enables growth in terms of use and ability of ANM systems to help meet the growing demands and expectations of our customers. | Continued improvement and use of ANM systems. | This will support growth in flexibility, dynamic management of our networks, and enables customer connections.
Coordination and cooperation activity | N/A | NGET/0057 | EPN,LPN,SPN | NGESO, NGET, connecting customers | Over the last years, there has been a significant increase in connections activity across the network, particularly on Generation with the UK transition to Net Zero. This additional activity has triggered the need for transmission reinforcement works at several Grid Supply Points. | In progress | Reviewed portfolios, identified three priority GSPs. | 2023-12-01 | Development plan for the GSP that takes into account all activity and future plans for the Distribution and Transmission networks, enabling the development of efficient and effective customer solutions. | N/A | N/A | N/A | Positive in terms of developing informed, cost efficient and whole system solutions that benefit customers across DNO and TO networks. | Positive for all parties involved. | Continue BaU and explore further opportunities for sharing knowledge, network information and facilitate closer interactions. | Clear benefits to all parties involved in meeting Distribution, Transmission and Grid Code obligations, connecting generation, facilitating Net Zero transition and in providing a whole system and cost efficient solutions.
Coordination and cooperation activity | NGED/0018 | N/A | NGED | 120 Local Authorities and SSE, UKPN, SPEN | Acting as a key stakeholder in Local Area Energy Planning in collaboration with other DNOs at network boundaries. Attending Local Authority meetings and supporting local decarbonisation projects including the development of Local Area Energy Plans. Ensuring local decarbonisation aspirations are captured within our DFES. | In progress | In 2023/24 all 120 Local Authorities in NGED licence area have been offered support with strategic local area decarbonisation planning (often in the form of Local Area Energy Planning). | 2023-01-04 | Ensuring we have the local information we need to create Network Development Plans that will support local decarbonisation and strategically invest in the network when and where it is needed at the lowest cost to customers. |  | Through our local engagement, 7,200 local projects have informed our DFES 2023 data. | https://www.nationalgrid.co.uk/dso/distribution-future-energy-scenarios | Our Local Authority engagement ensures that we are taking a whole system approach to local area decarbonisation helping achieve national Net Zero by 2050. These working groups bring together all key stakeholders at a local level. | The information we gather ensures we have the data we need to justify the right investment in our network, at the right time and in the right place. | Continue to engage with Local Authorities about their local decarbonisation plans and ensure these continue to inform our DFES and are therefore included in our strategic investment process. | The learning from local stakeholder data will help justify the need for network investment.
Related action | NGED/0018/A01 | N/A | NGED | 120 Local Authorities | [12 empty] | New website pages created and published that support local area decarbonisation planning. | 16/11/2023 | Completed | NGED/0018
NGET ACTIVITY AND ACTIONS THAT DON'T IMPACT NGED - Combine at the end

## User suggestions
Details of all proposals received during a relevant period from system users to advance the efficient and economical operation of Electricity Distributors’ and/or Transmission Owners’ networks. Details of any system user proposals that have been implemented (or are being implemented) as well as a concise and clear summary of proposals not deemed to be apt for implementation, including the reason(s) for that decision.
Unique identifier for each row of the sheet (starting with xxxx/U/001 where xxxx refers to the licensee) | Licensee who is publishing register | Licensees and other stakeholders with whom collaboration was/is being carried out. | domestic customer; customer commercial; Group of domestic customers; Group of commercial customers; local authority; combined authority; other infrastructure networks; generators; aggregators etc. | Date on which the user suggestion was received | Details of the suggestion. Only those suggestions that improve the economy and efficiency of the whole system is to be considered, suggestions benefitting just one user is not to be included. | Details of the relevance to whole system | Action taken based on the suggestion. Could even be decision to not take forward. | Justification of the action resulting from the user suggestion.
Unique id | Licensee | Collaborating licensees | User category | Suggestion submission date (mm/yyyy) | Description of the suggestion | Whole system relevance | Description of the action taken on the suggestion | Justification of the action
NGED/U/001 | NGED |  | Local authority | 2020-05-15 | Received a suggestion from Local Authorities as part of Distribution Future Energy Scenarios (DFES) stakeholder engagement to move from presenting data at Electricity Supply Area (ESA) level to also include a local authority breakdown. | By providing strategic forecast data in a more useful format to Local Authorities they are able to better inform their local energy plans, ensuing a coordinated approach to delivering net zero. Allowing stakeholders to interrogate and update them based on the specific technologies and scale of net zero challenges in their areas. | Improved the DFES process so that the granular spacial analysis for projecting growth under each scenario can be aggregated to either Electricity Supply Area (ESA) or Local Authority. | By providing our DFES scenario data in a way that is more useful to Local Authorities, we are ensuring better coordination between Local Area Energy Plans (LAEP) and our forecasting process.
NGED/U/002 | NGED | other DNOs | A wide range of stakeholder categories as part of Distribution Future Energy Scenario (DFES) annual stakeholder engagement in South West. A full breakdown of stakeholder categories can be found in the stakeholder reports: https://www.westernpower.co.uk/smarter-networks/network-strategy/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information As part of the 2021 DFES stakeholder engagement, an interactive webinar was run for each licence area where feedback from over 200 stakeholders was gathered through aggregated Mentie Meter polling and individual stakeholder comments. | South West - 22/06/2021 South Wales - 24/06/2021 East Midlands - 01/07/2021 West Midlands - 29/06/2021 2022 webinars 5/7/2022 - 14/7/2022 South West - 27/06/2023 South Wales - 27/06/2023 East Midlands - 30/06/2023 West Midlands - 30/06/2023 | Responses were sought on the near term factors impacting the uptake rate and spatial distribution of low carbon technologies, and how the unique characteristics of the licence area region would impact these. Suggestions that were actioned based on the feedback provided include: * Weighting rooftop solar distribution towards properties with a high uptake of EVs and affluence were updated based on feedback * Responses on our assumptions around pipeline and post-pipeline assessment of onshore wind projects. Particularly the view that South West wind development would pick-up sooner, between 2023 and 2027. * Highlighting need to assess other types of storage including molten salts. * Respondents expected co-location with renewables and serving industrial clusters to be the main business models for hydrogen electrolysis in the near and medium term. * Poll respondents thought that the recent lifting of the National Grid ‘Statement of Works’ in South Wales could result in a surge of thermal and flexible generation projects in the 2020s. * Stakeholders asked for additional information that we shared on the event and included in the core DFES publication. * Re-weighting carbon levies from electricity bills to gas bills would significantly reduce the cost of resistive electric heating. NGED received a high-level of agreement with the overall DFES approach and confirmed that a lot of the challenges raised are already captured in the existing process. This also provided valuable feedback from a diverse range of stakeholders that our DFES process is capturing the credible range of scenarios out to 2050. | By engaging with key stakeholder categories as part of the yearly DFES process, it means feedback can be gathered on the existing approach to identify where actions can be taken to improve the 2021 DFES publication. This helps capture changing markets, policy, technologies and ensures alignment with not just electricity, but the Whole Energy System. By having a licence area specific event it also helps with capturing geographic specific growth and Whole System integration challenges. | The suggestions and feedback we received as part of this workshop were reviewed and integrated into the DFES 2021 publication. Full details of the updated DFES can be found in in the 2021 DFES Technology Summary reports and Regional Review reports: https://www.westernpower.co.uk/smarter-networks/network-strategy/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information The datasets capturing these actions are available for download and are displayed on NGED's DFES map. | By actioning the suggestions made by stakeholders at this event, we are able to continually improve our DFES process. Making it more relevant, accurate and user friendly for stakeholders who use the available reports and datasets to inform their investment decisions. It allows NGED to more accurately forecast the credible range of growth across the South West, meaning they can develop and design a network that will not be a barrier to Net-Zero across the Whole Energy System.
NGED/U/003 | NGED |  | District Council | 2021-06-01 | Having attended one of NGED’s engagement workshops, a District Council reached out to us for support and guidance with Local Area Energy Plans (LAEP). Starting their net zero journey, they had strong aspirations but required a deeper understanding of the concept of LAEP and how the DFES process worked. Since this initial dialogue, NGED has supported them to achieve: * Unanimous agreement for production of an LAEP to be produced * More proactive energy planning rather than reacting to individual applications when submitted * Ongoing, two-way engagement with NGED’s expert forecasting team and their local Distribution Manager | The learning from this additional two-way engagement has been integrated into our DFES and stakeholder engagement to help us enable Councils and Local Authorities to develop coordinated LAEPs. | Engaged and provided information and feedback to enable a more ambition LAEP to be delivered. Enabling them to meet their net zero ambitions. | Supporting District Councils in delivering net zero and taking the learning from the two way engagement to benefit the Whole System.
NGED/U/004 | NGED | other DNOs | A stakeholder engagement webinar was hosted as part of the Network Development Plan (NDP) (electricity distribution standard licence condition SLC25B) to present methodology and format to stakeholders. A summary of the feedback can be found in the NDP methodology report: https://www.westernpower.co.uk/smarter-networks/network-strategy/network-development-plan | 2022-03-31 | Responses were sought on the analysis methodology and reporting format of the inaugural Network Development Plan publication, feedback collected using interactive polling of webinar attendees. Suggestions that have been actioned are listed below: * Poll respondents would benefit from additional clarification on the NDP purpose and how it relates to other DNO led planning activities. * Stakeholders broadly supported the range of publication formats, but indicated that a heat map of the results and a short video explaining results could increase data accessibility. NGED received a high-level of agreement with the overall NDP approach and confirmed that in particular the detailed analysis methodology accurately represents areas for network investment over a simplified approach to network analysis. | By engaging with key stakeholder categories as part of the NDP process, it means feedback can be gathered on the existing approach to identify how best the results can be presented in a way that stakeholders can access and understand. | The suggestions and feedback we received as part of this webinar were reviewed and included in the 2022 NDP publication. This also includes work within NGED to present NDP results in a heat map style format ahead of the 2024 NDP publication. | By actioning the suggestions made by stakeholders at this event, we are able to continually improve our NDP process. Making it more relevant, accurate and user friendly for stakeholders who use the available reports and datasets to inform their investment decisions.
NGED/U/005 | NGED | other DNOs | A wide range of stakeholder categories as part of Distribution Future Energy Scenario (DFES) annual stakeholder engagement in South West. A full breakdown of stakeholder categories can be found in the stakeholder reports: https://www.nationalgrid.co.uk/dso/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information As part of the 2022 DFES stakeholder engagement, an interactive webinar was run for each licence area where feedback from over 200 stakeholders was gathered through aggregated Menti Meter polling and individual stakeholder comments. | 2022 webinars - 4 webinars between 5/7/2022 - 14/7/2022 | Responses were sought on the near term factors impacting the uptake rate and spatial distribution of low carbon technologies, and how the unique characteristics of the licence area region would impact these. Suggestions that were actioned based on the feedback provided are listed in the DFES 2023 stakeholder consultation summary reports: https://www.nationalgrid.co.uk/dso/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information NGED received a high-level of agreement with the overall DFES approach and confirmed that a lot of the challenges raised are already captured in the existing process. This also provided valuable feedback from a diverse range of stakeholders that our DFES process is capturing the credible range of scenarios out to 2050. | By engaging with key stakeholder categories as part of the yearly DFES process, it means feedback can be gathered on the existing approach to identify where actions can be taken to improve the 2022 DFES publication. This helps capture changing markets, policy, technologies and ensures alignment with not just electricity, but the Whole Energy System. By having a licence area specific event it also helps with capturing geographic specific growth and Whole System integration challenges. | The suggestions and feedback we received as part of this workshop were reviewed and integrated into the DFES 2022 publication. Full details of the updated DFES can be found in in the 2022 DFES Technology Summary reports and Regional Review reports: https://www.westernpower.co.uk/smarter-networks/network-strategy/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information The datasets capturing these actions are available for download and are displayed on NGED's DFES map. | By actioning the suggestions made by stakeholders at this event, we are able to continually improve our DFES process. Making it more relevant, accurate and user friendly for stakeholders who use the available reports and datasets to inform their investment decisions. It allows NGED to more accurately forecast the credible range of growth across the South West, meaning they can develop and design a network that will not be a barrier to Net-Zero across the Whole Energy System.
NGED/U/006 | NGED | other DNOs | A wide range of stakeholder categories as part of Distribution Future Energy Scenario (DFES) annual stakeholder engagement in South West. A full breakdown of stakeholder categories can be found in the stakeholder reports: https://www.nationalgrid.co.uk/dso/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information As part of the 2023 DFES stakeholder engagement, an interactive webinar was run for each licence area where feedback from over 200 stakeholders was gathered through aggregated Menti Meter polling and individual stakeholder comments. | South West - 27/06/2023 South Wales - 27/06/2023 East Midlands - 30/06/2023 West Midlands - 30/06/2023 | Responses were sought on the near term factors impacting the uptake rate and spatial distribution of low carbon technologies, and how the unique characteristics of the licence area region would impact these. Suggestions that were actioned based on the feedback provided are listed in the DFES 2023 stakeholder consultation summary reports: https://www.nationalgrid.co.uk/dso/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information NGED received a high-level of agreement with the overall DFES approach and confirmed that a lot of the challenges raised are already captured in the existing process. This also provided valuable feedback from a diverse range of stakeholders that our DFES process is capturing the credible range of scenarios out to 2050. | By engaging with key stakeholder categories as part of the yearly DFES process, it means feedback can be gathered on the existing approach to identify where actions can be taken to improve the 2023 DFES publication. This helps capture changing markets, policy, technologies and ensures alignment with not just electricity, but the Whole Energy System. By having a licence area specific event it also helps with capturing geographic specific growth and Whole System integration challenges. | The suggestions and feedback we received as part of this workshop were reviewed and integrated into the DFES 2023 publication. Full details of the updated DFES can be found in in the 2023 DFES Technology Summary reports and Regional Review reports: https://www.westernpower.co.uk/smarter-networks/network-strategy/distribution-future-energy-scenarios/distribution-future-energy-scenarios-regional-information The datasets capturing these actions are available for download and are displayed on NGED's DFES map. | By actioning the suggestions made by stakeholders at this event, we are able to continually improve our DFES process. Making it more relevant, accurate and user friendly for stakeholders who use the available reports and datasets to inform their investment decisions. It allows NGED to more accurately forecast the credible range of growth across the South West, meaning they can develop and design a network that will not be a barrier to Net-Zero across the Whole Energy System.
NGED/U/007 | NGED | Other DNOs / GDNs | Local authority | 2023-04-01 | Through engagement with local authorities in the form of net zero surgeries, it was identified that it is challenging to find the relevant information for local area energy planning on our website. As a result, we commissioned a new hub on the website to point stakeholders in the right direction for being able to find the data and resources required to create their LAEP. | The creation of a LAEP is a key whole system output, and by providing the DNO-relevant datasets in an easy to find format this is facilitation of whole system outputs. | Website section created and published | supports whole system energy planning
NGED/U/008 | NGED | other DNOs | A stakeholder engagement webinar was hosted as part of the Network Development Plan (NDP) (electricity distribution standard licence condition SLC25B) to present methodology and format to stakeholders. A summary of the feedback can be found in the NDP methodology report: https://www.nationalgrid.co.uk/dso/network-development-plan | 2024-03-31 | Responses were sought on the analysis methodology and reporting format of the inaugural Network Development Plan publication, feedback collected using interactive polling of webinar attendees. Suggestions that have been actioned are listed below: * Poll respondents would benefit from having a way to identify which reports and relevant to their area (specifically local authority boundaries) * Poll respondents stated various other parts of the reports they would like to see included in detail, which we responded to in the methodology report and largely included within the specific network development reports. NGED received a high-level of agreement with the overall NDP approach and confirmed that in particular the detailed analysis methodology accurately represents areas for network investment over a simplified approach to network analysis. | By engaging with key stakeholder categories as part of the NDP process, it means feedback can be gathered on the existing approach to identify how best the results can be presented in a way that stakeholders can access and understand. | The suggestions and feedback we received as part of this webinar were reviewed and included in the 2024 NDP publication. | By actioning the suggestions made by stakeholders at this event, we are able to continually improve our NDP process. Making it more relevant, accurate and user friendly for stakeholders who use the available reports and datasets to inform their investment decisions.
NGED/U/009 | NGED | Other DNOs / GDNs | Local authority | ongoing throughout FY 23/24 | DSO has been continually engaging with the development of LAEPs across South Wales and other parts of our licence area (e.g. D2N2, Cornwall, the marches) to be forthcoming with feedback throughout the process of creating the LAEPs, which are whole system energy plans | The creation of a LAEP is a key whole system output, and by engaging with this, this is facilitation of whole system outputs. | Attendee to workshops, feedback on various reports and stages of development of the LAEPs | supports whole system energy planning
NGET/U/001 | NGET | UKPN | DNO | 2018-09-01 | Building a new GSP to reduce the need of replacing 132kV cables. | It is a process of whole system planning including both transmission and distribution networks. | A new Bengeworth Road substation on the London tunnel route in Lambeth is under construction. It is National Grid’s first SF6-free Gas Insulated Substation at 400kV in the UK. | It offers significant benefits to the London distribution network.
NGET/U/002 | NGET | All DNOs | DNO | 2024-04-01 | Having a land register for accessing land. | It is better way to share land data with the transmission and distribution systems. | NGET provided a land register to all the TOs and DNOs | It facilitates Net Zero transition by allowing all TOs and DNOs to access land data efficiently.

## Glossary
Acronym | Term
ANM | Active Network Management
BECCS | Bioenergy with Carbon Capture and Storage
CBA | Cost Benefit Analysis
CMP | CUSC Modification Proposal
CUSC | Connection and Use of System Code
DER | Distributed Energy Resource
DFES | Distribution Future Energy Scenarios
DIA | Distribution Impact Assessment
DNO | Distribution Network Operator
DSO | Distribution System Operator
ENA | Energy Networks Association
ESA | Electricity Supply Area
ESO | Electricity System Operator
FES | Future Energy Scenarios
FNB | Future Network Blueprint
HV | High Voltage
JSDL | Joint System Design Liaison
LFDD | Low-Frequency Demand Disconnection
LV | Low Voltage
NGED | National Grid Electricity Distribution
NGET | National Grid Electricity Transmission
NDP | Network Development Plan
NIA | Network Innovation Allowance
NIC | Network Innovation Competition
RDP | Regional Development Programme
SIF | Strategic Innovation Fund
SO | System Operator
SOW | Statement of Works
SPEN | SP Energy Networks
SSEN | Scottish and Southern Electricity Networks
SWOTS | South West Operational Tripping Scheme
TIA | Transmission Impact Assessment
TO | Transmission Operator
TPW | Third Party Works